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SECTION 1: REFORMS AND INVESTMENTS UNDER THE RECOVERY AND RESILIENCE PLAN 
1. Description of Reforms and Investments
A. COMPONENT 1.1: RESILIENT AND EFFECTIVE HEALTH SYSTEM, ENHANCED CIVIL PROTECTION
This component of the Cypriot recovery and resilience plan addresses the challenge of universal access to high-quality healthcare in Cyprus as well as civil protection’s overall emergency preparedness and response. The objective of this component is to strengthen the effectiveness, accessibility and overall resilience of the healthcare sector supporting the recently introduced National Health System through various interventions. These include the (i) modernisation and digitalisation of health care infrastructure and equipment, (ii) stepping-up of e-health services, (iii) accreditation of provided health care services and introduction of evidence-based clinical protocols and quality monitoring systems, as well as (iv) upskilling opportunities for health workers. It further aims at enhancing Cyprus’ civil protection system by establishing a modern Public Warning System.
The component addresses the country-specific recommendations on health (country-specific recommendation 1 of 2020 and country-specific recommendation 3 of 2019). 
 
A.1. 	Description of the reforms and investments for non-repayable financial support

Reform 1 (C1.1R1): National Centre for Clinical Evidence and Quality Improvement 
The objective of this reform is to enhance the quality and sustainability of the healthcare system. 
[bookmark: _Hlk235697303]This measure consists in a platform for clinical protocols, guidelines or pathways in medical care.

Reform 2 (C1.1R2): Electronic platform for the surveillance of Nosocomial Antibiotic Consumption and Healthcare-Associated Infections 
The objective of this reform is to support the digital transition and resilience of the healthcare sector.
This measure consists in an electronic platform to record data from hospital pharmacies, microbiology laboratories, and hospitals. 

Investment 1 (C1.1I1): Cyprus Blood Establishment 
The objective of this investment is to expand central Blood Establishment facilities in Cyprus.
This measure consists in the construction of facilities and purchase of equipment for Cyprus Blood Establishment. 
	
Investment 2 (C1.1I2): Cyprus public health information system 
The objective of this investment is to support public health sector bodies in making evidence-based decisions on epidemiological matters.
The measure consists in an influenza surveillance platform of the Cyprus Innovative Public Health Information and Communications Technology (ICT) System.

Investment 3 (C1.1I3): Support for the purchase of medical equipment in private hospitals
The objective of this investment is to modernise the medical equipment of private hospitals.
This measure consists in a financial support scheme for private hospitals to purchase medical equipment. 

Investment 4 (C1.1I4): Accreditation of health institutions
The objective of this investment is to support the accreditation of health institutions, enabling their registration within the National Health System (NHS) and enhancing the quality assurance of health care services provided.
This measure consists in a financial support scheme for the accreditation of health institutions.

Investment 6 (C1.1I6): Generic cross border e-health services in Cyprus
The objective of this investment is to support Cyprus’s cross-border exchange of patient health information within the EU.
This measure consists in support for cross-border patient data exchange with the Member States in the eHealth Digital Service Infrastructure (eHDSI).
 
Investment 7 (C1.1I7): Public warning system for emergency operations 
The objective of this investment is to enhance Cyprus’ civil protection system by establishing a public warning system for alerting on emergencies.
This measure consists in a public warning system through mobile phones.
 
Investment 5 (C1.1I5): Construction works and new equipment in Cyprus State Hospitals 
The objective of this investment is to finance construction works and new equipment of Cyprus State Hospitals.
This measure consist in construction works or purchase of equipment for Cyprus State Hospitals.

Reform 3 (C1.1R3): Healthcare provision and reimbursement using value-based models
The objective of this reform is to change the reimbursement system for healthcare services.
The measure consists in value-based reimbursement in the General Health System. 
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A.2. 	Milestones, targets, indicators, and timetable for monitoring and implementation for non-repayable financial support
	Sequential Number
	Related Measure (Reform or Investment)
	Milestone/Target
	Name
	Qualitative indicators 
(for milestones)
	Quantitative indicators 
(for targets)
	Indicative timeline for completion
	Description of each milestone and target

	
	
	
	
	
	Unit of measure
	Baseline
	Goal
	Quarter
	Year
	

	2b
	C1.1R1
National Centre for Clinical Evidence and Quality Improvement
	Milestone
	[bookmark: _Hlk235697377]Platform for clinical protocols, guidelines or pathways 
	Platform accessible
	-
	-
	-
	Q4
	2025
	[bookmark: _Hlk235697449]An e-learning platform including at least 90 clinical protocols, guidelines or pathways, is accessible. The contractor shall certify that the clinical protocols, guidelines or pathways have been peer reviewed.

	3
	C1.1R2
Design of an Electronic platform for the surveillance of Nosocomial Antibiotic Consumption and Healthcare – Associated Infections 
	Milestone
	Adoption of the list of health care facilities 
	Adoption of the list of health care facilities 
	-
	-
	-
	Q1
	2023
	Adoption of the list of healthcare facilities that shall be providing information to the Ministry of Health on antibiotic consumption and healthcare-associated infections that shall be monitored by the Ministry of Health. 

	4
	C1.1R2
Electronic platform for the surveillance of Nosocomial Antibiotic Consumption and Healthcare- Associated Infections 
	Milestone 
	Electronic platform 
	Electronic platform accessible
	-
	-
	-
	Q4
	2025
	An electronic platform to record data from hospital pharmacies (nosocomial antibiotic consumption), microbiology laboratories (antimicrobial resistance), and hospitals (healthcare-associated infections (HAIs)) shall be accessible. 

	5
	C1.1I1
New facilities for the Cyprus Blood Establishment and procurement of the latest technology attendant equipment
	Milestone
	Contract signature for the construction of the Cyprus Blood Establishment
	Signature of the contract
	-
	-
	-
	Q3
	2022
	Signature of the contract with the selected tenderer(s) (contractor(s)) selected under a competitive call for tenders for the construction of the Cyprus Blood Establishment.

	6
	C1.1I1
Cyprus Blood Establishment 
	Milestone
	Blood establishment facilities and equipment
	Facilities constructed and equipment purchased
	-
	-
	-
	Q2
	2025
	The Cyprus Blood Establishment facilities are constructed and equipment is purchased. The new facilities shall have a primary energy demand that is at least 20% lower than defined in the nearly zero-energy building (NZEB) requirement. 

	7

	C1.1I2
Cyprus Innovative Public Health information and communications technology (ICT) System 
	Milestone
	Influenza Sentinel Surveillance (ISS)System 
	Fully operational system
	-
	-
	
	Q2
	2022
	The Influenza Sentinel Surveillance System module of the Cyprus Innovative Public Health information and communications technology (ICT) System shall be operational and a system monitoring its effectiveness shall be in place.

	8
	C1.1I2
Cyprus Public Health information System
	Target
	Sentinels registered in the module
	 -
	Number
	0
	30
	Q2
	2024
	At least 30 doctors are registered as sentinels in the influenza surveillance module of the Cyprus Public Health Information System. 

	9
	C1.1I3
Purchase/replacement of medical equipment in hospitals
	Target
	Health institutions having benefitted from the financial support scheme 
	 -
	Number
	0
	10
	Q4
	2023
	At least ten of the applicant health institutions of various categories have received financial support from the scheme for medical equipment acquisition. 

	10
	C1.1I3
Support for the purchase of medical equipment in private hospitals
	Target
	Private hospitals purchased medical equipment with funding from the financial support scheme
	 -
	Number
	10
	23
	Q4
	2025
	At least 23 private hospitals have received financial support from the scheme to purchase medical equipment. 

	12
	C1.1I4
Accreditation of health institutions
	Target
	Health institutions have received financial support for their accreditation 
	-
	Number
	0
	30
	Q2
	2026
	At least 30 health institutions have received financial support from the scheme and been accredited based on International Society for Quality in Healthcare (ISQua) standards. 

	13
	C1.1I6
Deployment of generic cross border e-health services in Cyprus
	Milestone
	Completion of the analysis, design, and development phase of the IT System for cross-border e-health services
	Completion of the analysis, design, and development phase of the IT System, as provided in a dedicated report by the deliverables acceptance team in the contracting authority
	-
	-
	-
	Q4
	2023
	The analysis, design and development of the IT System phase shall be completed. 
Specifications shall include: 

a) Service Location and capability lookup Profile / the Cross-Community Patient Discovery Profile (to locate communities that hold patient relevant health data and the translation of patient identifiers across communities holding the same patient’s data). 
b) open source National Contact Point (OpenNCP) update that supports the eHDSI Automatic Data Collection (eADC). 
c) Update Patient Summary (PS-A), e-Prescription (eP), e-Dispencing (eD), unstructured clinical documents, and patient access to cross border data services, based on Wave 6 Clinical Document Architecture (W6 CDA) Implementation Guidelines by the e-Health network.

	14
	C1.1I6
Generic cross border e-health services in Cyprus
	Milestone
	Cross-border patient data exchange 
	System for the exchange of patient data accessible
	-
	-
	-
	Q2
	2025
	System for the exchange of patient data between Cyprus and Member States of the European Union in the eHDSI is accessible, which may include but it is not limited to the following functionalities: e-prescription, e-dispensation, and patient summary. Additionally, the service for the unstructured original clinical documents is approved. 

	15
	C1.1I7
Public warning system for emergency operations 
	Milestone
	Public warning system ready for pilot operation 
	“Contractor’s correction report after final testing and final tests results report” issued by the contractor
	-
	-
	-
	Q4
	2025
	The public warning system through mobile phones is ready for pilot operation and evidenced by the “contractor’s correction report after final testing and final tests results report”.

	17
	C1.1I5 Construction works and new equipment in Cyprus State Hospitals
	Target
	Construction works or purchase of equipment in Cyprus State hospitals
	
	Number
	0
	4
	Q2
	2024
	Construction works or purchase of equipment in the following hospital units: (1) COVID-19 unit at Famagusta Hospital; (2) Mental Health Hospital; (3) Invasive Radiology Unit: (4) Paphos General Hospital.
The Mental Health Hospital shall have a primary energy demand that is at least 20% lower than defined by the nearly zero-energy building (NZEB) requirement.

	18
	C1.1I5 Construction works and new equipment in Cyprus State Hospitals
	Target
	Construction works or purchase of equipment in Cyprus State hospitals 
	
	Number
	4
	11
	Q2
	2026
	Construction works or purchase of equipment in the following hospital units: (1) Haemodyalisis Units at Paphos and Limassol Hospitals; (2) Neurology clinic at Nicosia General Hospital; (3) Stroke unit at Nicosia General Hospital; (4) Health Center at Akaki, (5) Accident and Emergency Units at Nicosia General Hospital; (6) Accident and Emergency Units at Paphos General Hospital and (7) Larnaca General Hospital. 
The Haemodyalisis Unit at Paphos Hospital, and the Health Center at Akaki shall have a primary energy demand that is at least 20% lower than defined by the nearly zero-energy building (NZEB) requirement. 
Purchase of equipment by the State Health Services Organization (SHSO-OKYPY).

	16
	C1.1R3
Healthcare provision and reimbursement using value-based models.
	Milestone
	Value-based reimbursement for primary and in-patient care 
	Value-based reimbursement for primary and in-patient care published
	-
	-
	-
	Q4
	2024
	Health Insurance Organisation (HIO) publishes the criteria and indicators of value-based reimbursement for primary and in-patient care. The publication may include, for example, circulars and announcements. HIO decision(s) concerning the reimbursement of healthcare providers within the framework of the General Healthcare System are published in the official gazette.
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B. COMPONENT 2.1: CLIMATE NEUTRALITY, ENERGY EFFICIENCY AND RENEWABLE ENERGY
This component of the Cypriot recovery and resilience plan aims to address the challenge of climate change mitigation by contributing to the country’s transition to climate neutrality. 
The objectives of the component are to improve the environment policy through measures relating to green taxation, the opening up of the electricity market and the facilitation of licensing of renewable energy and renovation projects. The component aims to improve the energy efficiency of the building stock and other infrastructure and to support green investments for SMEs, households, the wider public sector, and NGOs. The component also targets the alleviation of energy poverty and aims to address Cyprus’ energy isolation.
The component supports addressing the Country Specific Recommendations for the years 2019 and 2020 that recommend focusing investment and investment-related policies on energy efficiency and renewable energy (Country-Specific Recommendation 4 of 2019 and Country-Specific Recommendation 3 of 2020).
It is expected that no measure in this component does significant harm to environmental objectives within the meaning of Article 17 of Regulation (EU) 2020/852, taking into account the description of the measures and the mitigating steps set out in the recovery and resilience plan in accordance with the DNSH Technical Guidance (2021/C58/01).

B.1. 	Description of the reforms and investments for non-repayable financial support
Reform 1 (C2.1R1): Green Taxation
The objective of this reform is to support a more efficient use of environmental resources, reduce greenhouse gas emissions and to increase the penetration of renewable energy. 
This measure consists in the entry into force of legal acts on a carbon tax on transport fuels, a charge on the landfill of municipal waste, an increase of existing water fees and tax incentives for enterprises and individuals.

Reform 2 (C2.1R2): Independence of Cyprus Transmission System Operator (TSOC) from the incumbent Electricity Authority of Cyprus
The objective of the measure is to enhance competition in the electricity market by creating conditions for new investors to participate in the generation, storage, aggregation, demand response and supply of electricity.
The reform shall consist in ensuring the independence of the Cyprus Transmission System Operator (TSOC) from the incumbent Electricity Authority of Cyprus (EAC) in terms of governance, financial and personnel management. The measure shall also facilitate supplier switching, which is expected to reduce the cost of electricity for domestic and commercial/industrial customers.
The implementation of the reform shall be completed by 31 December 2021.

Reform 3 (C2.1R3): Digital One-Stop Shops to streamline RES projects permitting and to facilitate Energy Renovation in Buildings
The objective of the measure is to promote the implementation of RES projects by streamlining the RES projects permitting process. The reform shall also aim at accelerating the energy renovation of buildings. 
The reform shall consist in digitalising the licensing permitting process for RES projects and establishing a single point of contact for technical and financial support for the purposes of energy renovation of buildings.
The implementation of the reform shall be completed by 31 December 2022.

Reform 4 (C2.1R4): Energy Storage Regulatory Framework
The objective of the measure is to establish a regulatory framework for promoting the participation of storage facilities in the electricity market.
The reform shall consist in amending the Transmission and Distribution Rules (TDRs) and the Trading and Settlement Rules (TSRs) to allow storage facilities to participate in the wholesale electricity market. This shall promote the generation of electricity from renewable energy systems and to contribute to the efficiency and economic viability of the electricity market as a whole.
The implementation of the reform shall be completed by 31 December 2021.

Investment 1 (C2.1I1): Energy-saving investments in SMEs and non-profit organisations 
The objective of this investment is to reduce the primary and final energy consumption and the CO2 emissions in buildings and/or facilities owned or operated by SMEs and non-profit organisations.
This measure consists in support for building renovation and for making production processes use less energy. 
Investment 2 (C2.1I2): Promoting renewables and individual energy efficiency measures in dwellings and tackling energy poverty, including in households with vulnerable electricity consumers 
The objective of the measure is to encourage the use of renewable energy sources and energy savings by the large stock of old dwellings, as well as to subsidise the implementation of small-scale energy renovations in households with vulnerable electricity consumers including energy-poor households and people with disabilities.
This measure consists in providing grants for renewables and individual energy efficiency measures. 
Investment 3 (C2.1I3): Facilitating the transition of local communities towards climate investments 
The objective of this investment is to facilitate the transition of local communities towards climate mitigation and adaptation.
The measure consists in a grant scheme for energy and climate adaptation investments in Local (Community) Councils. 

[bookmark: _Hlk213777844]Investment 5 (C2.1I5): Energy efficiency investments in public buildings
The objective of this investment is to facilitate energy efficiency investments in public buildings.
This measure is composed of two energy efficiency investments: (i) Fire Service Properties and Schools; and (ii) Nicosia General Hospital.

Investment 6 (C2.1I6): Expansion of the renewable energy and smart grids testing infrastructure at the University of Cyprus
The objective of this investment is to expand the existing renewable energy and smart grids testing infrastructure at the University of Cyprus and to connect it with the existing grid.
This measure consists in commissioning renewable energy and smart grids equipment. 

Investment 7 (C2.1I7): Mass installation by the Distribution System Operator (DSO) of Smart Metering Infrastructure (Advanced Metering Infrastructure)
The objective of this investment is to facilitate the mass roll-out of smart meters in Cyprus. 
This measure consists in the delivery of 400 000 smart meters to the Electricity Authority of Cyprus and the installation of 200 000 smart meters.

Investment 8 (C2.1I8): Monitoring and reduction of GHG emissions in agriculture
The objective of this investment is to monitor greenhouse gas emissions from agricultural activities in Cyprus, with a view to reducing GHG emissions in agriculture.
The investment consists in a GHG monitoring system. 

Investment 9 (C2.1I9): Fire protection
The objective of this investment is to support the capabilities of authorities in Cyprus to cope with fire hazards and to invest in the protection against the risks faced by citizens, infrastructure, and forests.
This measure consists in the purchase of a firefighting aircraft, vehicles, and equipment 

Investment 10 (C2.1I10): Market Management System (MMS) to facilitate the opening of the electricity market to competition
The objective of this investment is to introduce a Market Management System (MMS) by the Cyprus Transmission System Operator as a tool for facilitating the opening of the electricity market to competition.
This measure consists in the installation of the MMS marked by the first financial transactions taking place through the MMS, and the opening of Cyprus’ electricity market.
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B.2. 	Milestones, targets, indicators, and timetable for monitoring and implementation for non-repayable financial support
	Sequential Number
	Related Measure (Reform or Investment)
	Milestone / Target
	Name
	Qualitative indicators 
(for milestones)
	Quantitative indicators 
(for targets)
	Indicative timeline for completion
	Description of each milestone and target

	
	
	
	
	
	Unit of measure
	Baseline
	Goal
	Quarter
	Year
	

	19
	C2.1R1
Green Taxation 
	Milestone
	Entry into force of legal acts introducing a carbon tax on transport fuels, an increase of existing water fees, a charge on the landfill of municipal waste, and tax incentives for enterprises and individuals
	Provision in the legal acts indicating the entry into force 
	-
	-
	-
	Q2
	2026
	Entry into force of legal acts, which (a) introduce a carbon tax on transport fuels, (b) introduce an increase of existing water fees,(c) introduce a charge on the landfill of municipal waste, (d) introduce personal tax incentives for natural persons undertaking clean energy and electric mobility investments, and (e) introduce enhanced capital allowances for qualifying energy and climate-related capital expenditures by enterprises.

	21
	C2.1R2
Independence of Cyprus Transmission System Operator (TSOC) from the incumbent Electricity Authority of Cyprus
	Milestone
	Law for the Regulation of the Electricity Market of 2021
	Provision in the law indicating the entry into force of the 2021 "Law for the Regulation of the Electricity Market"
	-
	-
	-
	Q4
	2021
	Entry into force of the Law for the Regulation of the Electricity Market of 2021, which shall facilitate the opening of the electricity market to competition and boost the uptake of RES by: (a) achieving the independence of the Cyprus Transmission System Operator (TSOC) from the incumbent Electricity Authority of Cyprus (EAC) (autonomy in governance, financial autonomy and independence of TSOC personnel), (b) introducing the necessary steps for reducing the cost of electricity for domestic and commercial/industrial customers and (c) creating conditions of transparency and trust to motivate new investors in generation and supply of electricity.

	22
	C2.1R3
Digital One-Stop Shops to streamline RES projects permitting and to facilitate Energy Renovation in Buildings
	Milestone
	Fully operational IT platform 
	Fully operational IT platform accepted by the Ministry of Energy, Commerce, and Industry
	-
	-
	-
	Q4
	2022
	Fully operational IT platform for (1) guiding the applicant through the administrative permit application process in a transparent manner up to the delivery of one or several decisions by the responsible authorities, (2) providing the applicant with all necessary information and involve, where appropriate, other administrative authorities.

	23
	C2.1R4
Energy Storage Regulatory Framework
	Milestone
	Amendment of the Transmission and Distribution Rules (TDRs) and Trading and Settlement Rules (TSRs) 
	Publication on the website of the Cyprus Energy Regulatory Authority of Amendment of the Transmission and Distribution Rules (TDRs) and the Trading and Settlement Rules (TSRs)
	-
	-
	-
	Q4
	2021
	Entry into force of an amendment to the Transmission and Distribution Rules (TDRs) and Trading and Settlement Rules (TSRs) which shall provide the necessary regulatory framework (market rules) and technical modalities that shall allow storage facilities to: - participate in the wholesale electricity market, 
- promote the development of an economically viable, efficient, safe, and consumer-oriented electricity market that prioritises the generation of electricity from renewable energy systems.

	24
	C2.1I1
Promoting energy efficiency investments in SMEs and non-profit organisations
	Milestone
	Support scheme for Promoting energy efficiency investments in SMEs, municipalities, communities, and the wider public sector
	Publication of call for proposals for the support scheme for Promoting energy efficiency investments in SMEs, municipalities, communities, and the wider public sector
	-
	-
	-
	Q4
	2021
	Issue call for proposals for the support scheme for promoting energy efficiency investments in SMEs, municipalities, communities, and the wider public sector, following verification of state aid regulation to be applied by Commissioner for State Aid Control and Council of Ministers’ decision approving the scheme’s objectives. The investment shall aim at achieving on average at least a 30% primary energy demand reduction.

	26
	C2.1I1
Energy saving investments in SMEs, and non-profit organisations
	Target
	Energy saving projects in buildings
	 
	Number
	0
	275
	Q4
	2025
	Energy Performance Certificates or declarations from a qualified expert or energy auditor on achieved energy savings issued for 275 energy saving projects. 

	27
	C2.1I2
Promoting renewables and individual energy efficiency measures in dwellings and tackling energy poverty in households with vulnerable electricity consumers 
	Milestone
	First call for proposals for Promoting renewables and individual energy efficiency measures in dwellings 
	First call for proposals published
	-
	-
	-
	Q2
	2021
	The first call for proposals for promoting renewables and individual energy efficiency measures in dwellings has been published on the RES and Energy Conservation Fund website. The investment shall aim at achieving on average at least a 30% primary energy demand reduction.

	28a
	C2.1I2
Promoting renewables and individual energy efficiency measures in dwellings and tackling energy poverty in households with vulnerable electricity consumers 
	Target
	Dwellings and households with vulnerable electricity consumers (including people with disabilities) having improved their energy performance 
	 -
	Number
	0
	16 200
	Q4
	2023
	At least 16 200 dwellings, including 1 600 households with vulnerable electricity consumers (including people with disabilities), have improved their energy performance due to the financial support provided, with an objective to achieve on average at least a 30% primary energy demand reduction.

	28b
	C2.1I2
Renewables and individual energy efficiency measures in dwellings and tackling energy poverty in households with vulnerable electricity consumers
	Target
	Energy efficiency measures in dwellings 
	-
	Number
	16 200
	29 300
	Q2
	2026
	Reducing primary energy demand on average by at least 30% in 29 300 dwellings.

	30
	C2.1I3
Encouraging the use of renewables and energy savings by local/wider public authorities and facilitating the transition of local communities towards climate mitigation & adaptation
	Milestone
	First call for proposals to support local authorities in energy efficiency measures 
	Publish first call for proposals 
	-
	-
	-
	Q3
	2021
	The first call for proposals to support local authorities in energy efficiency measures has been published on the RES and Energy Conservation Fund Website. The investment shall aim at achieving on average at least a 30% primary energy demand reduction.

	32c
	C2.1I3
Facilitating the transition of local communities towards climate investments
	Target
	Grant scheme to support climate adaptation investments 
	Number
	-
	0
	27
	Q2
	2026
	Grants disbursed for at least 27 climate adaptation investments in Local (Community) Councils.

	35
	C2.1I5
Energy Efficiency Upgrading of public buildings
	Target
	Thermal insulation and photovoltaic systems installed in schools
	 -
	Number
	0
	405
	Q1
	2022
	Thermal insulation and photovoltaic systems installed in at least 405 schools with an objective to achieve on average at least a 30% primary energy demand reduction.

	36
	C2.1I5
Energy Efficiency Upgrading of public buildings
	Target
	Completion of set up and installation of photovoltaics system at the Nicosia General Hospital 
	-
	Number
	0
	943
	Q4
	2023
	Completion of set up and installation of PV system at the Nicosia General Hospital of total capacity of 943KW.

	37
	C2.1I5
Energy Efficiency investments in public buildings
	Target
	Installation of photovoltaic systems in Fire Service Properties
	-
	Number
	0
	650
	Q4
	2025
	Installation of photovoltaic systems, of a total capacity of 650KW, in Fire Service Properties.

	38
	C2.1I6
Upgrading renewable energy and smart grids testing infrastructure at the University of Cyprus
	Milestone
	Signature of contracts for the installation of equipment to upgrade the electricity grid into a smart grid
	Contracts Signature 
	-
	-
	-
	Q4
	2023
	Signature of contracts for the installation of equipment to upgrade the electricity grid into a smart grid following a successful public procurement procedure.

	39
	C2.1I6
Expansion of the renewable energy and smart grids testing infrastructure at the University of Cyprus
	Milestone
	Acceptance of renewable energy and smart grids testing equipment
	Issued acceptance certificate(s) 
	-
	-
	-
	Q4
	2024
	Acceptance certificate(s) issued, testifying commissioning and acceptance of the renewable energy and smart grids testing equipment.

	40
	C2.1I7
Mass installation by the Distribution System Operator (DSO) of Smart Metering Infrastructure (Advanced Metering Infrastructure)
	Milestone
	Contract Signature for smart electricity metering infrastructure 
	Contract Signature 
	-
	-
	-
	Q1
	2024
	Contract Signature for smart electricity metering infrastructure (Hardware, software, and support services).

	42
	C2.1I7
Mass installation by the Distribution System Operator (DSO) of Smart Metering Infrastructure (Advanced Metering Infrastructure)
	Target
	Acceptance and installation of smart meters
	 -
	Number
	0
	400 000 delivered to Electricity Authority of Cyprus

200 000 installed
	Q2
	2026
	Acceptance of 400 000 smart electricity meters by the Electricity Authority of Cyprus and installation of 200 000 of these.

	43
	C2.1I8
Monitoring and reduction of GHG emissions in agriculture
	Milestone
	Purchase and installation of monitoring units for measuring GHG emissions from agriculture
	Approval of the equipment and installation by the receiving committee 
	-
	-
	-
	Q2
	2023
	Purchase and installation of automobile unit and permanent monitoring units, for measuring GHG emissions from agriculture with the objective of implementing adequate policies to mitigate GHG emissions.

	44
	C2.1I8
Monitoring and reduction of GHG emissions in agriculture
	Target
	Reduction of GHG emissions from agriculture
	-
	% (Percentage)
	0
	10
	Q4
	2025
	Report confirming a 10% reduction of GHG emissions from agriculture. 

	45
	C2.1I9
Forests fire protection
	Milestone
	Signing of 8 Agreements/ Contract Signatures for the purchase of vehicles, equipment and provision of services and issue of call for tenders for the purchase of firefighting aircraft
	Signing of 8 Agreements/ Contract Signatures
	-
	-
	-
	Q2
	2022
	Signing of 8 Agreements/ Contracts Signatures with suppliers for the purchase of vehicles, equipment and provision of services and issue of call for tenders for the purchase of firefighting aircraft with the objective of contributing to climate change adaptation and to the reduction of the risk of explosion and expansion of forest fire and the strengthening protection against the risks faced by citizens, infrastructure and forests from a possible fire incident.

	47
	C2.1I9
Fire protection
	Milestone
	Acceptance of firefighting aircraft vehicles and equipment 
	Acceptance certificates issued for the delivery of firefighting aircraft vehicles and equipment 
	-
	-
	-
	Q2
	2026
	Acceptance certificates issued for the delivery of firefighting aircraft, vehicles and equipment. 

	48
	C2.1I10
Market Management System (MMS) to facilitate the opening of the electricity market to competition
	Milestone
	Installation of the Market Management System 
	Issuing of Final Acceptance Certificate for the Market Management System. 
	-
	-
	-
	Q1
	2023
	Installation of the Market Management System (MMS) for the Cyprus Electricity Market.

	48a
	C2.1I10
Market Management System (MMS) to facilitate the opening of the electricity market to competition
	Milestone
	First financial transactions of the MMS
	CERA Decision declaring the first day of electricity market trading, results of the electricity market for the first week of trading. 
	
	
	
	Q3
	2025
	Decision by CERA on the market operation evidenced by the first financial transactions performed through the MMS.
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C. COMPONENT 2.2: SUSTAINABLE TRANSPORT
This component of the Cyprus recovery and resilience plan aims to promote cleaner, smarter, safer, and fairer urban mobility by encouraging a modal shift to sustainable modes of transport, and to promote the use of zero or low-emission vehicles (LEVs) as well as the use of digital systems in the transport sector. 
The component addresses the country-specific recommendations on investment in sustainable transport (Country-Specific Recommendation 4 of 2019 and Country-Specific Recommendation 3 of 2020).
It is expected that no measure in this component does significant harm to environmental objectives within the meaning of Article 17 of Regulation (EU) 2020/852, taking into account the description of the measures and the mitigating steps set out in the recovery and resilience plan in accordance with the DNSH Technical Guidance (2021/C58/01). 

C.1. 	Description of the reforms and investments for non-repayable financial support
Reform 1 (C2.2R1): Installation of an Intelligent Transport System using Digital Twin technologies
The objective of this reform is to introduce smart features to technological infrastructure. 
This measure consists in installing an Intelligent Transport System. 

Reform 2 (C2.2R2): Entry into force of legal act(s) regarding electric vehicle (EV) recharging infrastructure
The objective of this reform is to establish electro-mobility infrastructure for recharging EVs.
This measure consists in the entry into force of legal act(s) on recharging infrastructure for EV. 

Reform 3 (C2.2R3): Entry into force of legal act(s) for the exclusion of polluting vehicles
The objective of this reform is to provide the regulatory framework to create incentives for replacing old and polluting vehicles, and for using sustainable commuting and mobility solutions.
This measure consists in the entry into force of legal act(s) allowing for the adoption of measures linked to the exclusion of polluting vehicles from certain areas. 

Investment 2 (C2.2I2): Creation of electro-mobility infrastructure
The objective of this investment is to create the necessary infrastructure to facilitate the transition to electro-mobility.
This measure is composed of three sub-measures:
Sub-measure 1: installation of publicly accessible EV charging stations and delivery of charging points used for EVs of the public sector fleet 
This investment consists in the installation of publicly accessible EV charging stations and the delivery of charging points used for EVs of the public sector fleet. 
Sub-measure 2: a grant scheme for the installation of publicly accessible charging points in the premises of businesses or local authorities
This scheme consists in support for the installation of charging points in the premises of businesses or local authorities. 
Sub-measure 3: a grant scheme for charging EVs from RES
This scheme consists in providing financial incentives to support charging of EVs from RES, including the installation of photovoltaic systems and charging equipment. 

Investment 3 (C2.2I3): Advance the use of Electric Vehicles (EVs)
The objective of this investment is the purchase of EVs, LEVs, electric bicycles and public or non-motorised modes of transport, while progressively phasing out older polluting vehicles from circulation. 
Sub-measure 1: kick-start the transition to electro-mobility in the public sector and local authorities 
This investment consists in the purchase of electric vehicles for the public sector.

Sub-measure 2: a support scheme for the purchase of EVs
This scheme consists in the purchase or registration of electric vehicles and electric bicycles. 

Sub-measure 3: a scrapping scheme for the most polluting vehicles combined with incentives for non/low emission mobility options
This scheme incentivises motorists to give up combustion engine vehicles in exchange for alternative mobility options, for example the purchase of a LEV or of an electric bicycle and/or free annual bus tickets. It also incentivises recycling of scrapped vehicles.

Investment 1 (C2.2I1): Sustainable Urban Mobility Projects (SUMP) and accessibility-enhancing measures
The objectives of this investment are to create the necessary infrastructure to enhance urban mobility with more environmentally friendly options and to increase the city environment and road safety. 


 
These measures consist in investments for the accessibility and safe movement of pedestrians, cyclists, and persons with disabilities in urban centres.
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C.2. 	Milestones, targets, indicators, and timetable for monitoring and implementation for non-repayable financial support
	Sequential Number
	Related Measure
(Reform or Investment)
	Milestone / Target
	Name
	Qualitative indicators 
(for milestones)
	Quantitative indicators 
(for targets)
	Indicative timeline for completion
	Description of each milestone and target

	
	
	
	
	
	Unit of measure
	Baseline
	Goal
	Quarter
	Year
	

	52
	C2.2R1
Installation of an Intelligent Transport System using Digital Twin technologies
	Target
	Installation and connection to the National Access Point of at least 150 sensors
	-
	Number
	0
	150
	Q1
	2024
	Acceptance certificates verifying the installation and connection to the National Access Point of a total of 150 traffic sensors 

	53
	C2.2R1
Installation of an Intelligent Transport System using Digital Twin technologies
	Target
	Installation and connection to the National Access Point of a total of 300 sensors
	-
	Number
	150
	300
	Q4
	2025
	Acceptance certificates verifying the installation and connection to the National Access Point of a total of 300 traffic sensors.

	54
	C2.2R2
Entry into force of legal act(s) regarding electric vehicle (EV) recharging infrastructure 
	Milestone
	Entry into force of legal act(s) related to electric vehicle charging points
	Entry into force of the legal act(s)
	-
	-
	-
	Q4
	2024
	Entry into force of legal act(s) regarding electric vehicle (EV) recharging infrastructure. 
The legal act(s) shall include a mechanism for the monitoring of the electric vehicle recharging infrastructure. 

	55
	C2.2R3
Progressively phase out the most polluting vehicles, especially in polluted urban areas
	Milestone
	Entry into force of the legislative act related to the phasing out of the most polluting vehicles
	Provision in the legislative act indicating the entry into force of the legislation
	-
	-
	-
	Q4
	2023
	Entry into force of the legislative act regarding the exclusion of polluting vehicles from areas or operations. 
The legislative act shall create the legal basis to enforce the adoption of restrictive measures related to the circulation of motor vehicles, with the aim to progressively phase out the most polluting vehicles.

	61
	C2.2I2
Creation of electro-mobility infrastructure
	Target
	Installation or delivery of charging points 
	-
	Number
	0
	1 000
	Q2
	2026
	Acceptance certificate or certificate of electrical installation, issued by the Electrical authority of Cyprus for the installation or delivery for at least 1 000 charging points.

	63a
	C2.2I3
Advance the use of Electric Vehicles (EVs)
	Target
	Purchase or registration of electric vehicles and electric bicycles
	-
	Number
	0
	4 412
	Q2
	2026
	Purchase or registration of at least 4 412 electric vehicles of categories M1, M2-3, N, L1e-L7e and electric bicycles.

	65
	C2.2I3
Advance the use of Electric Vehicles (EVs)
	Target
	Scrapping of high emission vehicles
	-
	Number
	0
	1 393
	Q2
	2026
	Completion certificate confirming the scrapping of at least 1 393 combustion engine vehicles replaced by electric bicycles, annual bus ticket(s) and low emission vehicles.

	58
	C2.2I1
Sustainable Urban Mobility Projects (SUMP) and accessibility enhancing measures
	Target
	 Construction work for at least 35km of sustainable transport routes
	-
	Number
	0
	35
	Q1
	2026
	Taking over certificates issued by the Contracting Authority confirming construction work for at least 35km of sustainable transport routes.
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D. COMPONENT 2.3: SMART AND SUSTAINABLE WATER MANAGEMENT 
This component of the Cypriot recovery and resilience plan addresses inefficiencies in water management. The objectives of this component are to ensure supply of good quality drinking water, maximising the infrastructure for sewerage collection systems, sewerage treatment and reuse of treated effluent in agriculture, reducing water loss, non-revenue water and groundwater abstraction, improving anti-flood infrastructure, improving operational efficiency of the services being provided to the consumers through technological advances and establishing transparency in financial transactions.
The component addresses the Country Specific Recommendation on water management (Country-Specific Recommendation 3 of 2020 and Country-Specific Recommendation 4 of 2019). 
It is expected that no measure in this component does significant harm to environmental objectives within the meaning of Article 17 of Regulation (EU) 2020/852, taking into account the description of the measures and the mitigating steps set out in the recovery and resilience plan in accordance with the DNSH Technical Guidance (2021/C58/01). 

D.1. 	Description of the reforms and investments for non-repayable financial support
Reform 1 (C2.3R1): Water Resource Management Reform
The objective of this investment is to define actions addressing structural weaknesses in the water resource management in Cyprus. 
The reform consists in the adoption of an action plan on water resource management. 

Investment 2 (C2.3I2): Water Treatment Plants
The objective of this investment is to support projects in water treatment plants.
The measure consists in projects in the water treatment plants of Limassol, Asprokremmos, Tersefanou, Kornos and Kannaviou. 

Investment 3 (C2.3I3): Integrated Monitoring and Control Management System for the Water Development Department’s infrastructure
The objective of this investment is to support the Water Development Department (WDD). 
The measure consists in a Monitoring and Control Management System for the WDD.

Investment 4 (C2.3I4): Smart Water and Sewerage Networks Management
The objective of this investment is to support management and energy efficiency of the water network of Larnaca and Limassol.
The measure consists in sensors, smart meters, and digital twin decision support system(s). 

Investment 5 (C2.3I5): Anti-flood and water collection measures
The objective of this investment is to mitigate the negative effects from flooding events. 
The measure consists in anti-flood work(s) or reconstruction or construction of streets and pavements, and in landscaping of flood channel(s). 

Investment 6 (C2.3I6): Water security projects
The objective of this investment is ensuring water security of Nicosia, Limassol and Klavdia.
The measure consists in water reservoir(s) and a water treatment plant.

Investment 8 (C2.3I8) Protection of the marine ecosystem from hazards through oil spills
The objective of the measure is to protect marine ecosystems through an upgrade of the operational capacity of the Department of Fisheries and Marine Research to respond promptly, adequately, and effectively to incidents from oil pollution to marine pollution.
The measure consists of the purchase of three antipollution vessels with the possibility of autonomous oil recovery operations, two of which shall operate close to the shoreline and the larger one on the high seas, as well as the purchase of two autonomous oil dispersant air spraying units.
The implementation of the investment shall be completed by 31 December 2025.
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D.2. 	Milestones, targets, indicators, and timetable for monitoring and implementation for non-repayable financial support
	Sequential Number
	Related Measure (Reform or Investment)
	Milestone / Target
	Name
	Qualitative indicators 
(for milestones)
	Quantitative indicators 
(for targets)
	Indicative timeline for completion
	Description of each milestone and target

	
	
	
	
	
	Unit of measure
	Baseline
	Goal
	Quarter
	Year
	

	66
	C2.3R1 
Water Resource Management Reform
	Milestone
	Adoption and publication of an action plan on water resource management
	Adoption and publication of the action plan on the website of the Ministry of Agriculture, Rural Development and Environment
	-
	-
	-
	Q2
	2025
	Adoption by the Council of Ministers and publication on the website of the Ministry of Agriculture, Rural Development and Environment of an action plan on water resource management. 

	70
	C2.3I2 
Water Treatment Plants 
	Milestone
	Projects in Water Treatments Plant(s)
	Issued acceptance certificates
	
	
	
	Q4
	2025
	Projects in Water Treatment Plant(s) as follows:
Installation of activated carbon filtration system(s) in Tersefanou, Asprokremmos and Limassol
Installation of on-site chlorine dioxide generation system(s) in Limassol, Asprokremmos, Tersefanou, Kornos and Kannaviou
Installation of filtration system for the expansion of the Asprokremmos Water Treatment Plant including the motor control center. 

	71
	C2.3I3 
Integrated Monitoring and Control Management System for the Water Development Department’s infrastructure
	Milestone
	Completion of the detailed requirements analysis and system design document
	Approval of detailed requirements analysis and system design document by the Steering Committee of the Water Development Department 
	-
	-
	-
	Q2
	2022
	The requirements analysis and system design document shall describe all the aspects, features, and functionalities of the system, including quality sensors, operational sensors (such as flow, level, and pressure), energy meters, communications devices, IT equipment (hardware, software). The detailed requirements analysis and system design shall determine the exact number and type of equipment required for this project.

	74a
	C2.3I4
Smart Water and Sewerage Networks Management
	Target
	Delivery and installation of photovoltaics at the Larnaca Wastewater Treatment Plant
	
	Number
	0
	700
	Q1
	2023
	Delivery and installation of photovoltaic equipment at the Larnaca Wastewater Treatment Plant generating power of at least 700KW.

	76b
	C2.3I4
Smart Water and Sewerage Networks Management
	Milestone
	Projects in Larnaca and Limassol
	Issued acceptance certificates 
	-
	-
	-
	Q2
	2026
	Projects as follows:
a. At least 200 quality and pressure sensors and at least 100 000 smart meters for consumption reading. 
b. Digital Twin decision support system and smart water living lab in Limassol.
c. Digital Twin decision support system in Larnaca. 

	77a
	C2.3I5
Anti-flood and water collection measures
	Milestone
	Completion of construction works of drainage network and reconstruction of streets and pavements in areas of Nicosia
	Project management team certifies the completion of the construction
	-
	-
	-
	Q4
	2022
	Completion of construction of drainage network and reconstruction of streets and pavements in Agios Antonios, Old city, Likavitos and Agioi Omologites areas of Nicosia with a total length of approx. 6.5km.

	77b
	C2.3I5
Anti-flood and water collection measures
	Milestone
	Anti-flood work(s) 
or reconstruction or construction of streets and pavements in Nicosia and Limmasol
	Taking over certificates
	-
	-
	-
	Q2
	2026
	Anti-flood work(s) or reconstruction or construction of streets and pavements in Nicosia and Limassol.

	78
	C2.3I5
Anti-flood and water collection measures
	Milestone
	Construction works for rainwater collection and recycling in Kladeri area
	Taking over certificates
	-
	-
	-
	Q2
	2024
	Construction of rainwater collection and recycling system in Kladeri area.

	79
	C2.3I5
Anti-flood and water collection measures
	Milestone
	Landscaping of flood channel(s) in Livadia
	Taking over certificate
	
	
	
	Q4
	2025
	Landscaping of flood channel(s) in Livadia. 

	80
	C2.3I6
Water security projects
	Target
	Construction of two glass lined steel reservoirs in Nicosia district
	
	m3
	0
	16 000
	Q2
	2024
	Construction of two glass lined steel reservoirs in Nicosia District of a total capacity of 16 000m3.

	81
	C2.3I6
Water security projects
	Target
	Water reservoir(s) and water treatment plant
	
	m3
	16 000
	52 800
	Q2
	2026
	a. Two glass-lined steel water reservoirs in Nicosia 
b. one concrete water reservoir in Klavdia 
c. three water reservoirs in Limassol
d. water treatment plant in Limassol.
The total capacity of the water reservoirs in Nicosia, Larnaca and Limassol shall be at least 52 800m3.

	84
	C2.3I8 
Protection of the marine ecosystem from hazards through oil spills
	Milestone
	Delivery, quality inspection to verify their operational effectiveness and acceptance of three vessels and two aerial spraying systems
	Expert’s reporting and issuance of quality certificate of the operational effectiveness and acceptance of vessels and aerial spraying systems
	-
	-
	-
	Q1
	2025
	Delivery, quality inspection to verify their operational effectiveness and acceptance of three vessels (one vessel of 25m in length approximately to operate within the Cypriot Exclusive Economic Zone and two vessels of 8-11m in length approximately to operate within coastal waters and two aerial spraying systems). 
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E. COMPONENT 3.1: NEW GROWTH MODEL AND DIVERSIFICATION OF THE ECONOMY
The component addresses the challenges of the Cypriot economy with regards to competitiveness, productivity, and investment, as well as overreliance on certain economic sectors, such as tourism. 
The objective of the component is to help the economy to transit to a new economic growth model (Sustainable Business and Trade Centre of Europe) by addressing sectoral challenges as follows:
Primary Sector: the objective is to develop a competitive agriculture sector primarily through agri-tech and strong collaboration with business, higher-education institutions, and research centres to excel.
Secondary Sector: the objective is to develop a competitive light manufacturing sector that includes a focus on areas such as green-tech and agri-tech. 
Sustainable Tourism: the objective is to develop a strong agri-tourism and sustainable hospitality infrastructure and attracting health & wellness tourists through competitive and reputable healthcare.
Circular economy (with emphasis on waste management): the objective is to help move towards a circular economy by making better use of raw materials, reducing waste, raising awareness for sustainable development and switching to renewable energy in order to mitigate the climate crisis, protect social well-being and build a resilient economy. The component contributes to addressing the country specific recommendation related to “focus investment on the green and digital transition” and “on waste and water management” (Country-Specific Recommendation 3 of 2020), “focus investment-related economic policy on sustainable transport, environment” and “on environment, in particular waste and water management” (Country-Specific Recommendation 4 of 2019)
It is expected that no measure in this component does significant harm to environmental objectives within the meaning of Article 17 of Regulation (EU) 2020/852, taking into account the description of the measures and the mitigating steps set out in the recovery and resilience plan in accordance with the DNSH Technical Guidance (2021/C58/01).

E.1. 	Description of the reforms and investments for non-repayable financial support
Sub-Component 3.1.1 Resilient and competitive primary sector

Reform 1 (C3.1R1): Move agricultural practices from the 20th century to the 21st century by investing in a national centre for excellence in agri-tech
The objective of the reform is to address challenges in the primary sector, including low productivity and lack of technological knowledge, by establishing a centralised operating model through strong collaboration between the Agricultural Research Institute and higher education institution(s). 
The reform aims to establish Cyprus’s Agricultural Research Institute as the country’s centre of excellence in agriculture, animal husbandry and environmental protection and to strengthen the cooperation between the Agricultural Research Institute and higher education institution(s) to develop new curriculum/a. 
The implementation of the reform shall be completed by 30 June 2023.

Reform 2 (C3.1R2): On-line platform for trade and information symmetry in the fresh produce supply chain
The objective of the reform is to address long-standing drawbacks of the fresh produce supply chain.
[bookmark: _Hlk213779189]The reform consists in the entry into force of a law on unfair practices in transactions in the local fresh produce market. A Platform shall be offered to Producers’ Organisations in the fresh produce market.

Reform 3 (C3.1R3): Genetic improvement of the Cyprus sheep and goat population 
The objective of this reform is to enhance the productivity and sustainability of the primary sector.
The reform consists in the support to farmers for the upgrade of the collection of data related to dairy production and the genomic identification of their sheep and goats. 

[bookmark: _Hlk189474712]Investment 2 (C3.1I2): Support of isotopic database of Cypriot food or drink products 
The objective of this investment is to create a blockchain-based verification methodology for the authentication of local products by using isotopic database(s). 
The measure consists in the purchase and installation of new Liquid Chromatography - Isotopic Ratio Mass Spectrometer (LC-IRMS) for isotopic characterisation; integrated isotopic DataBase(s) and blockchain system are connected for at least ten Cypriot food or drinks products. 

Investment 3 (C3.1I3): Upskill the existing farming community and professionalise future labour force by investing in human capital
The objective of the measure is the upskilling of the farming community, through knowledge transfer and the promotion of innovation. In this way, it aims at fostering a more competitive agricultural sector with higher potential, through capacity building and knowledge transfer. 

The investment shall consist in the granting of ten scholarships in the agricultural sector, of EUR 10 000 each, for supporting the development of the future labour force in the sector. It shall also support transfer of knowledge and innovation within the existing labour force, through the use of the Agricultural Knowledge and Innovation System with links to academia, bridging the gap between practical application on the one hand and knowledge, science, experience, and research on the other. 
The implementation of the investment shall be completed by 31 December 2022.

Sub-Component 3.1.2 Innovative and competitive secondary sector
Investment 5 (C3.1I5): Creation of a National Commercial Identity and promotion of the traditional product “halloumi”
The objective of the measure is to establish a brand name for the Cypriot products in order to promote their export.
The investment shall consist in the development of action plans based on two studies: (a) one on the creation of a National Commercial Identity “Made in Cyprus” (branding) focusing on the quality and structural characteristics of Cypriot products and services combined with elements of the tradition and history of the island, and (b) a study for implementing a strategy for halloumi cheese in order to increase its distinctiveness as an authentic Cyprus product and designing a promotional and awareness campaign.
The implementation of the investment shall be completed by 31 March 2022.

Investment 6 (C3.1I6): Scheme for supporting the production of enterprises in the agricultural sector
The objective of this investment is to support the resilience of the agricultural sector, diversification of economic activity, and incentivise investments in new businesses or in the technological advancement of existing businesses.
The measure consists in providing grants to enterprises in the agricultural sector to finance investments in their production capabilities.

Investment 7 (C3.1I7): Scheme for the competitiveness and/or the energy efficiency of large enterprises in Cyprus
The objective of this investment is to support investments by large enterprises, including production process, technological and energy efficiency.
The measure consists in the publication of the call for proposals and the signature of grant agreements with at least 10 enterprises. 

Sub-component 3.1.3 Sustainable, high value-added tourism
Investment 8 (C3.1I8): Added value of tourism 
The objective of this investment is to support tourism, attract new markets, reduce seasonality, and improve the built environment, especially in the countryside, mountainous and remote areas. 
This measure consists in signing grant agreements and issuing acceptance certificates or proof of payments for renovation works and equipment in the hospitality sector. 

Investment 9 (C3.1I9): Circular economy in hotels
The objective of this investment is to facilitate the transition of hotels’ business model to circular, or to launch circular products or services. 
This measure consists in certification. 

Investment 10 (C3.1I10): Enrichment of tourism 
The objective of this investment is to support the economy in rural, mountainous, and remote areas and to diversify tourism.
This measure consists in (i) the construction of the Aphrodite Route, and (ii) investments including, but not limited to, construction works, equipment, information and communication technologies, and advisory services for enterprises or local community boards. 

Sub-component 3.1.4 Circular economy
Reform 4 (C3.1R4): Circular economy 
The objective of this reform is to support the circular economy model in the country. 
The measure consists of an Action Plan and a grant scheme for business investment in the circular economy.

Reform 5 (C3.1R5): Waste management coordination unit in the Department of Environment 
The objective of this reform is to monitor municipal waste management. 
This measure consists in a decision by the Council of Ministers on the framework for a unit for waste management coordination in the Department of Environment.

Investment 12 (C3.1I12): Waste management towards circular economy
The objective of this investment is to contribute to recycling of dry recyclables. This measure consists in the installation of 50 green kiosks for dry recyclables to help local authorities in remote areas to improve their waste management schemes.

Investment 11 (C3.1I11): Extension of the Cyprus Green Points Network 
The objective of this investment is the management of solid waste and the protection of the environment and public health. 
This measure consists in the construction or extension of six Green Points to deposit specific household or municipal waste streams. 
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E.2. 	Milestones, targets, indicators, and timetable for monitoring and implementation for non-repayable financial support
	Sequential Number
	Related Measure (Reform or Investment)
	Milestone / Target
	Name
	Qualitative indicators 
(for milestones)
	Quantitative indicators 
(for targets)
	Indicative timeline for completion
	Description of each milestone and target

	
	
	
	
	
	Unit of measure
	Baseline
	Goal
	Quarter
	Year
	

	85
	C3.1R1
Move agricultural practices from the 20th century to the 21st century by investing in a national centre for excellence in agri-tech
	Milestone
	Cooperation between the Agricultural 
Research Institute and higher education institution(s), for at least one MSc programme
	Entry into force of signed cooperation agreement(s)
	-
	-
	-
	Q4
	2022
	Entry into force of legally binding document(s) establishing the collaboration for at least one MSc programme signed between the Agricultural Research Institute and higher education institution(s).

	86
	C3.1R1
Move agricultural practices from the 20th century to the 21st century by investing in a national centre for excellence in agri-tech
	Milestone
	Master in the wider domain of Agriculture
	Media announcement and communication by competent authorities 
	-
	-
	-
	Q2
	2023
	Enrolment of students and start of a Master in the wider domain of Agriculture.

	87
	C3.1R2
On-line platform for improving the trade and information symmetry in the fresh produce supply chain
	Milestone
	Law on unfair practices in transactions in the local fresh produce market
	Provision in the law indicating the entry into force of the new law on unfair practices in transactions in the local fresh produce market
	-
	-
	-
	Q2
	2022
	Entry into force of a new law which shall address unfair trading practices in transactions in the local fresh produce market, such as unilateral and retroactive amendments to contracts, last-minute cancellations, payment deadlines longer than 30 days, payment for damaged or unsold products and other actions affecting those involved in the production and distribution chain of agricultural products.

	88
	C3.1R2
On-line platform for trade and information symmetry in the fresh produce supply chain
	Milestone
	Platform for recording transactions in the local fresh produce market
	Platform available to Producers’ Organisations
	-
	-
	-
	Q2
	2024
	Online Platform for recording transactions in the fresh produce market shall be available to Producers’ Organisations.

	90
	C3.1R3
Genetic improvement of the Cyprus sheep and goat population
	Milestone
	Genomic identifications registered in ARI database. 
	Aid disbursed and genomic identifications registered in ARI database. 
	
	
	
	Q2
	2026
	Aid has been disbursed to farmers for the upgrade of the collection of data related to dairy production. Genomic identifications for at least 15 000 unique sheep and goats have been registered in ARI (Agricultural Research Institute) database.

	93
	C3.1I2
Enhancement of isotopic database of traditional Cypriot products
	Milestone
	Liquid Chromatography- Isotopic Ratio Mass Spectrometer (LC-IRMS) equipment
	Signed statement of the acceptance of equipment to the standard quality and time specified in the tender documents and the signed contract
	-
	-
	-
	Q4
	2021
	Purchase and Install New Liquid Chromatography- Isotopic Ratio Mass Spectrometer (LC-IRMS) equipment for isotopic characterisation.

	94
	C3.1I2
Support of isotopic database of Cypriot food or drink products
	Target
	Products connected to the system
	-
	Number
	0
	10
	Q1
	2025
	Integrated Isotopic DataBase(s) and blockchain system are connected for at least ten Cypriot food or drinks products. 

	95
	C3.1I3
Upskill existing and future farmers
	Target
	Scholarships granted
	-
	Number
	0
	5
	Q4
	2022
	At least five scholarships granted to secondary school graduates to study degree courses related to agriculture, in cooperation with the Department of Agriculture, the Agricultural Research Institute and local universities.

	97
	C3.1I5
Creation of a National Commercial Identity and promotion of the traditional product “halloumi”
	Milestone
	Action Plans for (a) the “made in Cyprus” branding, and (b) for the promotion of the halloumi cheese
	Publication of the Council of Ministers’ decision and of the action plan
	-
	-
	-
	Q1
	2022
	Adoption by the Council of Ministers of Action Plans that shall consist of: 
(1) assisting businesses to promote their products and services on the basis of the “made in Cyprus” branding, and
(2) increasing the distinctiveness of the halloumi cheese as an authentic Cyprus product and designing a promotional and awareness campaign for it.

	99
	C3.1I6
Scheme for supporting the production of enterprises in agricultural sector 
	Target
	Grant agreements signed with enterprises in the agricultural sector 
	-
	Number
	0
	120
	Q1
	2026
	Signature of grant agreements with at least 120 enterprises in the agricultural sector for supporting their production capabilities. 

	100
	C3.1I7
Scheme for the competitiveness and/or the energy efficiency of large enterprises in Cyprus
	Milestone
	Start of the grant scheme on large enterprises 
	Publication of the call for proposals on the Ministry website
	-
	-
	-
	Q3
	2023
	Following scheme approval by the Council of Ministers, issuance of call for proposals for the award of grants to large enterprises to expand existing business through investments that enhance the technological level, the production process, and their productivity, as well as to undertake investments that improve their energy performance. The terms of reference including eligibility criteria that ensure that the selected projects comply with the ‘Do no significant harm’ Technical Guidance (2021/C58/01) through the use of an exclusion list and the requirement of compliance with the relevant EU and national environmental legislation.

	102a
	C3.1I7
Scheme for the competitiveness and/or the energy efficiency of large enterprises in Cyprus
	Target
	Grant agreements signed with enterprises
	-
	Number
	0
	10
	Q2
	2026
	Signature of grant agreements with at least 10 enterprises. 

	103
	C3.1I8
Added value of tourism 
	Target
	Grant agreements signed with enterprises in the hospitality sector
	-
	Number
	0
	186
	Q2
	2024
	Signature of grant agreements with at least 186 enterprises in the hospitality sector.

	104
	C3.1I8
Added value of tourism 
	Target
	Grant to hotels or other tourism establishments 
	-
	Number
	0
	36
	Q2
	2026
	Signature of grant agreements with at least 36 hotels or other tourism establishments for renovation, refurbishing and/or equipment. 

	104c
	C3.1I8
Added value of tourism 
	Milestone
	Renovation works and equipment for Filoxenia Conference Centre
	Acceptance certificate(s) or proof of payment
	-
	-
	-
	Q4
	2025
	Acceptance certificate(s) or proof of payment for renovation works and equipment for Filoxenia Conference Centre

	105
	C3.1I9
Promotion of circular economy in hotel establishments
	Target
	Coaching scheme for circular economy
	-
	Number
	0
	50
	Q2
	2022
	Signed collaboration agreements with at least 50 hotels have been signed for tailored business coaching for circular economy.

	106
	C3.1I9
Circular economy in hotel establishments
	Target
	Certified circular hotels 
	-
	Number
	0
	18
	Q1
	2026
	At least 18 hotels certified as circular hotels according to the national certification scheme national standards.

	107
	C3.1I10
Enrichment of tourism 
	Milestone
	Aphrodite Route
	Taking-over certificate 
	-
	-
	-
	Q1
	2024
	Taking-over certificate for construction works for the Aphrodite Route.

	108
	C3.1I10
Enrichment of tourism 
	Target
	Investments, including but not limited to construction works, equipment, information and communication services, and advisory services. 
	-
	Number
	0
	200
	Q4
	2025
	Investments, including but not limited to construction works, equipment, information and communication technologies, and advisory services in at least 200 enterprises or local community boards.

	109
	C3.1R4
Enhancement of circular economy in the Industry
	Milestone
	Approval of the National Action Plan for the Enhancement of Circular Economy in Cyprus 
	Publication of the Council of Ministers’ decision for the approval of the National Action plan.
	-
	-
	-
	Q4
	2021
	Approval, by the Council of Ministers, of the National Action Plan for the Enhancement of Circular Economy in Cyprus 

	110
	C3.1R4
Circular economy 
	Target
	Signed grant agreement with companies which are moving into a circular operating model
	-
	Number
	0
	25
	Q2
	2026
	Signature of grant agreements with at least 25 companies moving to a circular operating model

	111
	C3.1R5 
Waste management coordination unit in the Department of Environment
	Milestone
	Waste management coordination unit
	Publication of the Council of Ministers Decision
	-
	-
	-
	Q2
	2025
	Approval of the waste coordination unit in the Department of Environment by the Council of Ministers.

	112
	C3.1I12
Waste management towards circular economy 
	Milestone
	Signature of the contract for the installation of Green kiosks
	Signature of the contract
	-
	-
	-
	Q3
	2023
	Signed contract for the set up and installation of at least 50 Green kiosks for dry recyclables. 

	115
	C3.1I12
Waste management towards circular economy 
	Target
	Installation of green kiosks 
	-
	Number
	0
	50
	Q4
	2025
	At least 50 green kiosks are installed.

	116b
	C3.1I11
Extension of the Cyprus Green Points Network 
	Target
	Construction or extension of six Green Points 
	-
	Number
	0
	6
	Q2
	2026
	Six Green Points are constructed or extended.
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F. COMPONENT 3.2: ENHANCED RESEARCH AND INNOVATION
The component of the Cypriot recovery and resilience plan addresses the challenges that Cyprus faces as regards the Research and Development ecosystem that plays a relatively limited role in economic growth. This is mainly due to a low share of Science, Technology, Engineering and Math (STEM) graduates, limited interaction of the public research system with the business sector and limited access and availability of risk funding. 
The objectives of the component are to strengthen links between research organisations and enterprises, commercialise research results, increase intensity in research & development (R&D) activity and investments by both public and private organisations, as well as to make all publicly funded research infrastructure accessible to the entire ecosystem. Furthermore, it aims to enhance financial support to start-ups, scale-ups, SMEs, internationalise the local research and innovation (R&I) ecosystem, develop local talent and attract talent from abroad to work in R&I with emphasis on specific thematic areas. 
The component addresses the Country-Specific Recommendations on increasing the focus on investment-related economic policy on research and innovation (Country-Specific Recommendations 3 of 2020 and 4 of 2019).
It is expected that no measure in this component does significant harm to environmental objectives within the meaning of Article 17 of Regulation (EU) 2020/852, taking into account the description of the measures and the mitigating steps set out in the recovery and resilience plan in accordance with the DNSH Technical Guidance (2021/C58/01).
F.1. 	Description of the reforms and investments for non-repayable financial support

Reform 1 (C3.2R1): National Research and Innovation Policy 
The objective of the reform is to support the R&I Ecosystem.
This measure consists in the adoption of the R&I Strategy and the Action Plan. 

Reform 2 (C3.2R2): Incentives to encourage and attract investments and human capital in Research and Innovation
The objective of the measure is to attract investment in innovative companies and entrepreneurial and scientific talents from abroad.
The reform shall consist in the extension of the application of the tax scheme for investing in innovative companies to legal entities (from physical persons currently). Eligible investments of up to EUR 150 000 per investor, under this incentive, include equity, loans, guarantees and factoring. In addition, it shall consist in the review, promotion and, where appropriate, amendment of current incentive schemes aimed at attracting talents from third countries, including the Scientific VISA scheme for researchers and their families and the Start-up VISA scheme for founders of innovative enterprises and their families.
The implementation of the reform shall be completed by 30 September 2022.

Reform 3 (C3.2R3): Support access to publicly funded research infrastructure 
The objective of the reform is to support access to publicly funded research infrastructure. 
This measure consists in the publication of the National Policy of the Republic of Cyprus for Open Science Practices.

Investment 1 (C3.2I1): Set up a central knowledge transfer office (cKTO)
The objective of the investment is to support academia-business collaboration and commercialisation of research results to enhance technology transfer in Cyprus. 
This measure consists in a central Knowledge Transfer Office.

Investment 2 (C3.2I2): Innovation funding programmes 
The objective of the investment is to support enterprises and start-ups on R&I activities and to support research organisations to create open access research infrastructures.
This measure consists in projects on R&I activities.

Investment 3 (C3.2I3): R&I funding programme on green transition
The objective of the investment is to support projects on green transition activities. 
This measure consists in projects on green transition R&I activities.

Investment 4 (C3.2I4): Funding schemes for R&D activities on dual-use technologies and classified laboratories
The objective of the investment is to support dual-use technologies, which would otherwise only serve government/military purposes, for civilian, commercial and societal interests.
The measure consists in the signature of grant agreements and the issuing of facility security clearance certificates.
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F.2. 	Milestones, targets, indicators, and timetable for monitoring and implementation for non-repayable financial support
	Sequential Number
	Related Measure (Reform or Investment)
	Milestone / Target
	Name
	Qualitative indicators 
(for milestones)
	Quantitative indicators 
(for targets)
	Indicative timeline for completion
	Description of each milestone and target

	
	
	
	
	
	Unit of measure
	Baseline
	Goal
	Quarter
	Year
	

	120
	C3.2R1
National R&I Policy and policy tools
	Milestone
	Adoption of the national R&I Strategy and of the Action Plan to implement it
	Publication of the Council of Ministers’ decision
	-
	-
	-
	Q4
	2022
	Develop an integrated R&I Strategy, providing a long-term perspective framework, ensuring a focused effort and commitment for implementation, over time, on behalf of the State and stakeholders involved in the national R&I system, and a digital tool for the dynamic mapping of the R&I ecosystem.

	121
	C3.2R1
National Research and Innovation Policy 
	Milestone
	Performance-based funding mechanism; open access policy framework for publicly funded research and
technological infrastructure; framework for monitoring and coordinating the participation in ESFRI Landmarks
	Approval of a performance based funding-mechanism; publishing online an open access policy framework for publicly funded research and
technological infrastructure; publishing online a framework
	-
	-
	-
	Q2
	2026
	Approval by the Council of Ministers of a performance-based funding mechanism for publicly funded research organizations, which may include but is not limited to the Centers of Excellence. 

Publishing online an open access policy framework for publicly funded research and technological infrastructure, which may include but is not limited to access condition(s) and pricing.
Publishing online a framework for monitoring and coordinating the participation in European Strategy Forum on Research Infrastructures (ESFRI) Landmarks.

	122
	C3.2R2
Incentives for investments and human capital in R&I
	Milestone
	Tax exemption of legal entities for investing in innovative companies
	Provision in the law indicating the entry into force of the legislation
	-
	-
	-
	Q1
	2022
	Entry into force of a law establishing the tax exemption of corporate investors (legal entities) for investing in innovative companies.

	123
	C3.2R3
Policies to foster access to publicly funded research infrastructure and laboratories
	Milestone
	Digital registry to record and publish research infrastructure 
	Link to the digital registry published in the Deputy Ministry for Research, Innovation and Digital Policy website
	-
	-
	-
	Q4
	2022
	Development and start of operation of a digital registry to record and publish research infrastructure that shall facilitate the request of access of interested parties to such infrastructure. It shall include the mapping of all publicly funded research institutions (under Horizon 2020, national schemes). It shall also improve visibility of the Research Institutions and support collaboration with the private sector. 

	124
	C3.2R3
Support access to publicly funded research infrastructure 
	Milestone
	National Policy of the Republic of Cyprus for Open Science Practices
	Publication of the National Policy of the Republic of Cyprus for Open Science Practices
	-
	-
	-
	Q4
	2024
	Publication of the National Policy of the Republic of Cyprus for Open Science Practices.

	125
	C3.2I1
Set up and operate a central Knowledge Transfer Office (KTO)
	Milestone
	Launch of KTO 
	Opening of KTO’s first case
	-
	-
	-
	Q2
	2022
	The Research and Innovation Foundation, responsible for putting in operation the KTO, has hired or contracted highly trained staff and/or experts to provide expert knowledge transfer services. Systems and tools shall be in place to support KTO operation. The KTO shall start the provision of services to universities, other research organisations or enterprises.

	126
	C3.2I1
Set up a central Knowledge Transfer Office (cKTO)
	Target
	Progress report on the provision of knowledge transfer support services 
	-
	Number
	0
	30
	Q4
	2025
	Progress report issued by META, on the provision of knowledge transfer support services for at least 30 projects. 

cKTO business plan issued by the Research and Innovation Foundation (RIF), which may include but is not limited to a SWOT analysis.

	127
	C3.2I2
Innovation funding programmes for start-ups, innovative companies, and SMEs
	Milestone
	Signature of grant agreements for 50% of budget
	Grant agreements signed
	-
	-
	-
	Q4
	2022
	Signing of grant agreements which commit at least 50% of total budget (contracts of a total value of at least EUR 26 000 000 total budget) for innovation funding programmes for start-ups, innovative companies and SMEs, with terms of reference including eligibility criteria that ensure that the selected projects comply with the ‘Do no significant harm’ Technical Guidance (2021/C58/01) through the use of an exclusion list and the requirement of compliance with the relevant EU and national environmental legislation.

	128
	C3.2I2
Innovation funding programmes for start-ups, innovative companies, and SMEs
	Target
	Completed projects to carry out R&I related activities
	-
	Number
	0
	70
	Q3
	2023
	At least 70 completed projects to carry out R&I related activities. 

	129
	C3.2I2
Innovation funding programmes 
	Target
	Projects on R&I activities
	-
	Number
	70
	231
	Q2
	2026
	Reports issued by the RIF for at least 231 projects on R&I activities. 

	130
	C3.2I3
R&I funding program on green transition
	Milestone
	Signature of grant agreements for a R&I funding programme of EUR 6 million budget
	Grant agreements signed by the Director of the Research and Innovation Foundation
	-
	-
	-
	Q4
	2022
	Signing of grant agreements for the selected proposals to be funded under a R&I funding program on green transition, with a total budget of EUR 6 million, with terms of reference including eligibility criteria that ensure that the selected projects comply with the ‘Do no significant harm’ Technical Guidance (2021/C58/01) through the use of an exclusion list and the requirement of compliance with the relevant EU and national environmental legislation.

	131a
	C3.2I3
R&I funding program on green transition
	Target
	Projects on green transition R&I activities
	-
	Number
	0
	10
	Q2
	2026
	Reports issued by the RIF for at least 10 projects on green transition R&I activities. 


	132
	C3.2I4
Funding to organisations performing R&D activities on dual technologies
	Milestone
	Signing of grant agreements which commit 80% of total budget for funding to organisations performing R&D activities on dual technologies
	Grant agreements signed
	-
	-
	-
	Q2
	2023
	Signing of grant agreements which commit 80% of total budget (contracts of at least a total value of 2 400 000 euro total budget) for funding to organisations performing R&D activities on dual technologies, with terms of reference including eligibility criteria that ensure that the selected projects comply with the ‘Do no significant harm’ Technical Guidance (2021/C58/01) through the use of an exclusion list and the requirement of compliance with the relevant EU and national environmental legislation.

	133
	C3.2I4
Funding schemes for R&D activities on dual-use technologies and classified laboratories 
	Target
	Facility security clearance certificates 
	-
	Number
	0
	16
	Q2
	2026
	At least 16 facility security clearance certificates issued. 
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G. COMPONENT 3.3: BUSINESS SUPPORT FOR COMPETITIVENESS
This component of the Cypriot Recovery and Resilience plan addresses the challenges of low productivity and competitiveness of the economy, driven by the enterprises’ small size on average, the complex licensing process requested for an investment and difficulties of access to funding to business. The objectives of this component are to support entrepreneurs and enterprises and improve their competitiveness and contribution to the growth of the economy by improving the regulatory framework regarding investment and entrepreneurial activity and to enhance SMEs productivity, mainly through digitalisation. It consists of six reforms and four investments, to be completed by Q2 2026.
The component addresses the Country-Specific Recommendation 3 of 2020 and Country-Specific Recommendation 4 of 2019. 

G.1. 	Description of the reforms and investments for non-repayable financial support
Investment 1 (C3.3I1): Information system for the Department of Registrar of Companies and Intellectual Property.
The objective of this investment is to support and digitalize the Department of Registrar of Companies and Intellectual Property.
This measure consists in a Registry Platform for the Companies Section of the Department of Registrar of Companies and Intellectual Property and trainings being provided.

Reform 1 (C3.3R1): Facilitation of Strategic investments
The objective of the measure is to develop a new system supporting strategic investments, aiming at stimulating investment activity in the country through streamlined rules and mechanisms, simplifying the licencing and permit procedures, reducing the administrative burden, and making the strategic investment environment more efficient. The definition of strategic investment refers to investments in strategic sectors (including Health and Social Care, Education, Culture, Sport, Environment, Industry, Tourism, Energy, Research, Development, and Innovation) that significantly contribute to the development of the economy.
The reform shall consist in the entry into force of a legislation for the facilitation of strategic investments, in regards to the efficiency of obtaining investment licenses and building permits. A dedicated governmental sector shall be assigned for the processing of strategic investments. It shall consist in the preparation of the operational guidelines, process flows, and other ISO 9001:2015 requirements for mainstreaming the process. It shall develop Memorandum of Understandings with other Departments relevant to parts of the process in order to ensure the fast-track mechanism’s feasibility. Moreover, it shall include training of employees in the procedures to be introduced. In addition, the reform shall benefit from the set-up of a digital platform that shall enable applying, studying, and issuing Planning and Building Permits digitally, through an application management tool and a GIS system (project under Component 3.4: “enhancing e-system for issuing building permits”). 
The implementation of the reform shall be completed by 30 June 2023.

Reform 2 (C3.3R2): Supporting Fast-Track Business Activation Mechanism
The objective of this reform is the digitalisation of business support.
This measure consists in an interactive digital platform for business support being accessible. 

Reform 7 (C3.3R7): Screening of Foreign Direct Investment 
The objective of this reform is to establish a mechanism for assessing foreign direct investment in the economy. 
This measure consists in the entry into force of a Foreign Direct Investment screening law.

Reform 4 (C3.3R4): National Promotional Agency
The objective of this reform is to facilitate access to finance for enterprises.
This measure consists in the appointment of the Board of Directors of a National Promotional Agency (NPA). 

Reform 6 (C3.3R6): Incentives to promote mergers & acquisitions
The objective of the measure is to incentivise the increase of SMEs’ size.
The reform shall consist in targeted incentives to promote the mergers or acquisitions of enterprises in order to scale-up and become more competitive. In particular, the reform shall consist in the approval of a report and an accompanying action plan by the Council of Ministers, following the evaluation of similar regimes within the EU and consultation with stakeholders for specific incentives for promoting mergers and acquisitions.
The implementation of the reform shall be completed by 31 December 2022.

Investment 2 (C3.3I2): A Regulatory Sandbox 
The objective of the measure is to allow companies to test products and services in a controlled environment. 
The investment consists in a Regulatory Sandbox for Fintech, start-ups, and other companies.

Investment 4 (C3.3I4): Scheme for the digital upgrade of enterprises 
The objective of this reform is to support the integration of digital technology in enterprises established in Cyprus.
This measure consists in the provision of grants for digital investments of enterprises.

Investment 6 (C3.3I6): State funded equity fund 
The objective of this investment is the support of access to alternative sources of finance. 
This measure consists in the incorporation of an equity fund.

Reform 8 - (C3.3R8): The Provision of Crowdfunding Services for Business Law 
The objective of the reform is to foster a secure and transparent crowdfunding environment, promoting alternative sources of financing opportunities for start-ups and SMEs, while maintaining high standards of investor protection.
The reform consists in the entry into force of the Provision of Crowdfunding Services for Business Law.
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G.2. 	Milestones, targets, indicators, and timetable for monitoring and implementation for non-repayable financial support
	Sequential Number
	Related Measure (Reform or Investment)
	Milestone / Target
	Name
	Qualitative indicators 
(for milestones)
	Quantitative indicators 
(for targets)
	Indicative timeline for completion
	Description of each milestone and target

	
	
	
	
	
	Unit of measure
	Baseline
	Goal
	Quarter
	Year
	

	134
	C3.3R1
Facilitation of Strategic investments
	Milestone
	Law for strategic investments
	Provision in the law indicating the entry into force of the law
	-
	-
	-
	Q1
	2022
	Entry into force of a law supporting strategic investments in Cyprus which shall include the following elements: streamlining of procedures for licencing strategic investment, project manager for each project, timely issuance of building permits.

	135
	C3.3R1
Facilitation of Strategic investments
	Milestone
	Organisational capacity’s enhancement for the facilitation of strategic investments
	Publication in the official gazette the setup of a government sector facilitating the reform, and of the process system and guidelines, and stated verification by the coordinating authority of training completion
	-
	-
	-
	Q2
	2023
	Publication in the official gazette of the completion of the setup of a sector in the Department of Town Planning and Housing for the enhancement of the facilitation of strategic system; publication of the process system and of the guidelines design; and reporting by the Coordinating authority of key personnel training for the implementation of the reform.

	136
	C3.3R2
Enhancing Fast-Track Business Activation Mechanism
	Milestone
	Establishment of an electronic system where investors can submit their online application 
	Announcement by the Ministry of Commerce of the electronic system accepting applications
	-
	-
	-
	Q4
	2022
	Upgrade of the services of applications for business permit issuance, guidance for establishment and operation, provision of information for all the necessary permits required by the company to start operations, facilitation for the issuance of residence and employment permits in Cyprus for third-country nationals, application for registration as a foreign interest company through the establishment of an electronic system where investors may submit their online application.

	137
	C3.3R2
Supporting Fast-Track Business Activation Mechanism
	Target
	Investment application assessment through the platform
	 -
	Number
	0
	35
	Q4
	2025
	Assessment of at least 35 applications for investment through the platform.

	138a
	C3.3R7 Screening of Foreign Direct Investment
	Milestone
	Entry into force of the legal act(s) on foreign Direct Investment screening 
	Entry into force of the legal act(s)
	-
	-
	-
	Q2
	2026
	Entry into force of the legal act(s) on the foreign Direct Investment screening. 

	140
	C3.3R4
Design and establish a National Promotional Agency 
	Milestone
	Approval by the Council of Ministers of the roadmap for the creation and establishment of a National Promotional Agency
	Publication of the Council of Ministers’ decision
	-
	-
	-
	Q2
	2023
	Approval by the Council of Ministers of the roadmap for the creation and establishment of a National Promotional Agency which shall facilitate access to loans and guarantees to Small and Medium Enterprises and enhance the absorption capacity of EU financing through EU tools.

	141
	C3.3R4
National Promotional Agency 
	Milestone
	Cyprus National Promotional Agency
	Appointment of the Board of Directors
	
	
	
	Q3
	2025
	Appointment of the Board of Directors of the National Promotional Agency published in the Official Gazette of the Republic of Cyprus.

	142a
	C3.3R8
The Provision of Crowdfunding Services for Business Law
	Milestone
	Entry into force of legal act(s) on the Provision of Crowdfunding Services for Business Law 
	Provision in the law indicating the entry into force of legal act(s)
	-
	-
	-
	Q4
	2024
	Entry into force of the legal act(s) on the Provision of Crowdfunding Services for Business. 

	143
	C3.3R6
Incentives to promote mergers and acquisitions.
	Milestone
	Action Plan for incentives for mergers and acquisitions
	Council of Ministers adoption of a report and the accompanying action plan
	-
	-
	-
	Q4
	2022
	Approval of a report and an accompanying action plan by the Council of Ministers on specific incentives for promoting mergers and acquisitions, following the evaluation of similar regimes within the EU and consultation with stakeholders. 

	144
	C3.3I2
A Regulatory Sandbox 
	Milestone
	Regulatory Sandbox 
	Regulatory Sandbox is accessible. 
	-
	-
	-
	Q2
	2024
	A Regulatory Sandbox is accessible.

	147
	C3.3I4
Scheme for the digital upgrade of enterprises 
	Milestone
	Publication of call for proposals following approval of the scheme by the Council of Ministers
	Official announcement of the call for proposals in the press, the MECI/ITS website and MECI/ITS social media
	-
	-
	-
	Q2
	2023
	Publication of call for proposals for grants covering a percentage of expenditure that shall enhance the digital identity of the businesses or shall increase the amount of small and medium-size enterprises that use information and communication technologies (including the e-commerce sector), or shall promote digital entrepreneurship, following approval of the scheme for the digital upgrade of enterprises by the Council of Ministers. 

	148
	C3.3I4
Scheme for the digital upgrade of enterprises 
	Target
	Grant agreements signed 
	 -
	Number
	0
	290
	Q2
	2026
	Signature of grant agreements with at least 290 enterprises.

	151
	C3.3I6
State funded equity fund 
	Milestone
	Setup of the Fund 
	Registration of the Fund 
	-
	-
	-
	Q4
	2022
	The setup of the Fund is completed. The Fund shall increase the availability of alternative financing sources, particularly for innovative companies and start-ups. 

The investment policy shall include eligibility criteria for investees to ensure compliance with the ‘Do no significant harm’ Technical Guidance (2021/C58/01) of supported transactions under this measure through the use of sustainability proofing, the requirement of compliance with the relevant EU and national environmental legislation, and the requirement for beneficiaries that derived more than 50% of their revenues during the preceding financial year from activities or assets in the exclusion list to adopt and publish green transition plans.

	152
	C3.3I6
State funded equity fund 
	Target
	Investees supported through the Fund
	
	Number
	0
	7
	Q2
	2026
	At least 7 investees supported through equity financing by the Fund.

	153
	C3.3I1
Integrated Information system for the Department of Registrar of Companies and Intellectual Property
	Milestone
	System hardware, software, and networking installation 
	Certificate of receipt and acceptance issued
	-
	-
	-
	Q1
	2024
	Installation of system hardware, software, and networking.

	154
	C3.3I1
Information system for the Department of Registrar of Companies and Intellectual Property
	Milestone
	Training courses 
	Training courses given
	
	
	
	Q4
	2025
	Training courses given on the information system of the services which may include, but it is not limited to HE1-Registration of Company, HE4-Change of official particulars and HE57-Transfer of shares
of the Companies section of the Department of Registrar of Companies and Intellectual Property. 
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H. COMPONENT 3.4: MODERNISING PUBLIC AND LOCAL AUTHORITIES, MAKING JUSTICE MORE EFFICIENT AND FIGHTING CORRUPTION
This component of the Cypriot recovery and resilience plan addresses long-standing challenges in the functioning of public administration, at both the central and the local levels, the justice system, and the anti-corruption framework. The objectives of the component are: (i) to increase the effectiveness, efficiency and relevance of government processes, considering current challenges, needs, and expectations of citizens and businesses, (ii) to strengthen the administrative capacity and cooperation of the Ministry of Interior and local governments to ensure the effective implementation of the new local administration model, (iii) to improve the effectiveness, including quality and efficiency, of the justice system, through accelerating the administration of justice and reducing the backlog of cases, and (iv) to achieve greater coherence to the government’s efforts to fight corruption. 
The reforms and investments included in the component contribute to addressing the Country-Specific Recommendations on improving efficiency in the public sector, in particular as regards the functioning of the public administration and of local governments (Country-Specific Recommendations 1 of 2019 and 4 of 2020), on promoting flexible working arrangements (Country-Specific Recommendation 2 of 2020), on improving the efficiency and digitalisation of the judicial system (Country-Specific Recommendation 5 of 2019 and Country-Specific Recommendation 4 of 2020) and on anti-corruption reforms (Country-Specific Recommendation 5 of 2019).
 
H.1. Description of the reforms and investments for non-repayable financial support
Subcomponent 3.4.1: Modernising the Public Sector
Reform 1 (C3.4R1): Support the functioning of public administration. 
The objective of this reform is to support the human resource management within the general public administration and the administrative capacity of the Cyprus Police. This measure consists in (i) the adoption of measures on human resource management of the public administration; and (ii) the reorganisation and modernisation of the Cyprus Police by designing and implementing a new model of policing and operations.
 
Reform 2 (C3.4R2): Regulate flexible working arrangements in the public sector 
The objective of this reform is to allow for the use of flexible working arrangements. 
This measure consists in the entry into force of legal act(s) on flexible working arrangements in the public sector. 
 
Reform 3 (C3.4R3): Introduce new framework for evaluation and selection process for filling public service vacancies and new regulations for the evaluation of employees’ performance
The objective of this reform is to support the functioning of the public service.
This measure consists in the entry into force of legal act(s) on the recruitment, evaluation and promotion of civil servants.
 
Reform 4 (C3.4R4): Digitalisation of public procurement 
The objective of this reform is to introduce new procurement processes using digital tools. 
This measure consists in an online and accessible e-procurement system. 
 
Reform 5 (C3.4R5): Enhancement of the capacity of the Law Office 
The objective of the reform is to implement a digital transformation of the Law Office, aiming to increase its efficiency and effectiveness, as well as the productivity, quality of work and working conditions of the employees.
The reform shall consist in digitalising the processes and procedures of the Law Office by introducing an IT system (eLaw System). During the implementation of the project, a business analysis shall assess needs for process re-engineering.
The implementation of the reform shall be completed by 31 December 2023. 
 
Investment 3 (C3.4I3): Economic Policy Modelling Hub 
The objective of this investment is to increase the use of quantitative modelling techniques for policy impact assessment. 
This measure consists in the publication online of a report on the Project “Economic Policy Modelling Hub”.

Subcomponent 3.4.2: Local Administration and Spatial reform
Reform 6 (C3.4R6): New legal framework for Local Authorities and support measures 
The objective of this reform is to support the decision-making power, administrative autonomy, and efficiency of local authorities in Cyprus. 
This measure consists in the entry into force of legal act(s) on the organisation of local authorities in Cyprus and training. 
 
Reform 7 (C3.4R7): Urban land consolidation 
The objective of this reform is to reduce the pressure for municipalities’ expansion and increase soil seal.
This measure consists in (i) for the entry into force of a law on urban land consolidation and (ii) the publication of pilot urban land consolidation plans online. 

Investment 4 (C3.4I4): E-system for issuing building permits 
The objective of the investment is to increase the efficiency of building permit procedures. 
This measure consists in (i) expanding the e-application environment of the existing Hippodamos IT system for planning and permitting, to enable all planning authorities and building authorities (municipalities) to submit applications for planning and building permits from a common platform; (ii) additional services in the Hippodamos system. 
 
Investment 5 (C3.4I5): Smart cities 
The objective of this investment is to coordinate on-going smart cities initiatives.
This measure consists of a smart cities platform and mobile applications. 

Investment 6a (C3.4I6a): Regeneration and Revitalisation of Nicosia Inner City 
The objective of this investment is to revitalise the Nicosia inner city. 
This measure consists in renovating rooms in Nicosia.

Subcomponent 3.4.3: Efficient Justice System
Reform 8 (C3.4R8): Efficiency of Justice 
The objective of the reform is to reduce the high backlog of cases pending before the courts 
This measure consists in the reduction of the backlog of cases and appeals. 
 
Reform 9 (C3.4R9): Digital transformation of courts
The objective of this reform is to digitalise the justice system. 
This measure consists in the issuance of the temporary acceptance certificate of Phase One of the i-justice system. 
 
Investment 7 (C3.4I7): Training of judges
The objective of this investment is to address the low level of training and lifelong learning for judges. 
This measure consists in training of judges on the revised Civil Procedure Rules and other judicial skills.

Investment 8 (C3.4I8): Upgrading the infrastructure of courts
The objective of the investment is to address inefficiencies of the justice system caused by inadequate court buildings, both in terms of quantity and quality. 
The investment shall consist of the construction of an extension to the Famagusta District Court building. 
The implementation of the investment shall be completed by 31 December 2021.
 
Subcomponent 3.4.4: Fighting Corruption
Reform 10 (C3.4R10): Improving the legal and institutional framework for fighting corruption 
The objective of the reform is to achieve greater coherence in the fight against corruption by implementing the national horizontal action plan against corruption.
The reform shall consist of: (i) legislation to protect whistle-blowers, to enhance transparency in public decision-making processes and to prevent conflict of interest, (ii) establishment and operation of an independent authority against corruption, which shall coordinate the efforts of all bodies engaged in the fight against and prevention of corruption and shall supervise the timely implementation of actions by the different competent services (iii) anti-corruption public awareness and trainings and (iv) reinforcement of the Internal Audit Units in all the Ministries and the Internal Audit Service. 
The implementation of the reform shall be completed by 30 June 2024.
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H.2. 	Milestones, targets, indicators, and timetable for monitoring and implementation for non-repayable financial support
	Sequential Number
	Related Measure (Reform or Investment)
	Milestone/Target
	Name
	Qualitative indicators 
(for milestones)
	Quantitative indicators 
(for targets)
	Indicative timeline for completion
	Description of each milestone and target

	
	
	
	
	
	Unit of measure
	Baseline
	Goal
	Quarter
	Year
	

	155
	C3.4R1
Enhance the administrative capacity and improve the functioning of public administration for better policy making and implementation
	Milestone
	Action Plan on the efficient management of human resource issues in the national public administration 
	Adoption of the Action Plan by the Council of Ministers 
	-
	-
	-
	Q1
	2022
	The Council of Ministers has adopted an Action Plan that shall include:
- Guidelines, templates and implementation support by the Public Administration and Personnel Department (PAPD) to line ministries’ administration in relation to human resource management issues such as re-organisation and re-structuring, simplification of procedures and workforce planning.
- Implementation of a revised organisational structure of PAPD 
- Learning and Development Plan for PAPD staff.
- Training Plan for line ministries’ administration

	156
	C3.4R1
Enhance the administrative capacity and improve the functioning of public administration for better policy making and implementation
	Milestone
	New human resources management framework for Cyprus Police 
	Adoption by the Chief of Police 
	-
	-
	-
	Q4
	2023
	The new human resources management framework for Cyprus Police shall cover following areas: 
- Analysis and creation of job descriptions
- Recruitment
- Motivation
- Training and Development
- Compensation and Benefits
- Labour and employee relations and communication
- Management of retired members
- Safety and Health
- Human resource management strategy

	157
	C3.4R1
Support the functioning of public administration
	Milestone
	Guidelines and manuals, legal act(s), and trainings on management of human resources in the public administration
	Guidelines and manuals publicly online. Provision in the legal act(s) indicating their entry into force. Trainings provided.
	-
	-
	-
	Q4
	2025
	Guidelines and manuals on human resource management of public administration shall be publicly available online. 
Legal act(s) on disciplinary matters in the public administration shall enter into force. 
Trainings shall be provided to staff on human resource management of the public administration.

	158
	C3.4R2
Regulate flexible working arrangements in the public sector 
	Milestone
	Decision on flexible working arrangements in the public sector
	Decision by the Council of Ministers 
	-
	
	
	Q1
	2023
	A study regarding flexible working arrangements in the public sector shall be conducted. The PAPD shall assess the study’s recommendations considering appropriate safeguards aiming at improving the effectiveness of the public service. Following the assessment of the study’s recommendations, a decision regarding their implementation shall be taken by the Council of Ministers. 

	159
	C3.4R2
Regulate flexible working arrangements in the public sector 
	Milestone
	Flexible working arrangements
	Provision in the legal act(s) indicating their entry into force
	-
	-
	-
	Q4 
	2024
	Entry into force of legal act(s) on flexible working arrangements in the public sector.

	160
	C3.4R3
Introduce new framework for evaluation and selection process for filling public service vacancies and new regulations for the evaluation of employees’ performance
	Milestone
	Entry into force of legislation for the evaluation and selection process for public service vacancies and regulations for employees’ performance evaluation. 
	Provision in the relevant law(s) and regulations indicating their respective entry into force 
	-
	-
	-
	Q4 
	2021
	The main elements shall be:
(i) entry into force of a law providing for the evaluation and selection of candidates to fill the public service promotion posts, including managerial posts, with new criteria and methods based on objective assessment and merit, and amendment of the Public Service Law where deemed necessary, and 
(ii) entry into force of new regulations for implementing a new performance appraisal system for public employees, to be used for development and promotion purposes in order to make the performance appraisal procedure and the promotion mechanism more transparent, fair, skill-based and effective

	162
	C3.4R4
Digitalisation of public procurement 
	Milestone
	E-procurement system 
	E-procurement system accessible
	-
	-
	-
	Q4
	2025
	The e-procurement system shall be online and accessible, with the following functionalities:
- statistical reporting 
- e-shopping through a digital catalogue. 

	163
	C3.4R5
Enhancement of the capacity of the Law Office 
	Milestone
	New IT system for the Law Office
	Entry into service of the new IT system
	-
	-
	-
	Q4
	2023
	The e- Law system is made operational for the Law Office and used. It includes the following functionalities:
- creation of electronic case files and folders, 
- case management and monitoring, 
- internal communication and workflows, 
- tracking of cases, financial management and payments, 
- digitalisation of paper files. Training of users has been concluded.
The paper files of the Law Office are digitalised.

	167
	C3.4I3
Economic Policy Modelling Hub 
	Milestone
	Setting up a Modelling Hub for Economic Policy Analysis
	Entry into service of the Hub
	-
	-
	-
	Q4
	2023
	Operationalisation and equipment of the Hub including appointment of the team of scientific staff. The team shall consist of experts on macroeconometric models, econometricians, data analytics experts and economists. 

	168
	C3.4I3
Economic Policy Modelling Hub 
	Milestone
	Report on the Project “Economic Policy Modelling Hub”
	Report on the Project “Economic Policy Modelling Hub” online
	
	
	
	Q4
	2025
	A report on the Project “Economic Policy Modelling Hub” shall be published online.

	169
	C3.4R6
New legal framework for Local Authorities and support measures 
	Milestone
	New legal framework on local authorities
	Provision in the law indicating the entry into force of legal act(s)
	-
	
	-
	Q2
	2024
	Entry into force of legal act(s) entailing:
- Reduction in the number of municipalities 
Establishment of community clusters 
- New framework for financing of municipalities 

	170
	C3.4R6
New legal framework for Local Authorities and support measures 
	Milestone
	Trainings 
	Trainings have taken place for local authorities
	
	
	
	Q4
	2024
	Trainings have taken place for local authorities. 

	171
	C3.4R7
Urban land consolidation 
	Milestone
	Entry into force of a law on urban land consolidation 
	Provision in the law indicating the entry into force of the law
	-
	-
	
	Q2
	2024
	Entry into force of the law on urban land consolidation. 

	172
	C3.4R7
Urban land consolidation 
	Target
	Number of plans for urban land consolidation 
	- 
	Number
	0
	10
	Q4
	2025
	Pilot plans for urban land consolidation have been published online 

	173
	C3.4I4
Enhancing e-system for issuing building permits 
	Milestone
	Enhancement of the e-application environment of the Hippodamos System
	Applications being received through the enhanced e-application environment
	-
	-
	-
	Q4
	2022 
	Completion of the enhancement of the e-application environment of the existing Hippodamos system to enable the submission of applications for planning and building permits for all planning authorities and building authorities (municipalities) from a common platform.

	174
	C3.4I4
E-system for issuing building permits 
	Milestone
	Planning and control tool, project management tool, software and hardware of Hippodamos 
	Services of the Hippodamos System
	-
	-
	-
	Q4
	2024
	The Hippodamos System shall include services which may include but are not limited to the following: 
· Electronic signature of documents
· Electronic Consultation.
Acceptance certificate(s) have been issued for the delivery of hardware consisting of at least two servers as specified in the contract.

	176
	C3.4I5
Smart cities 
	Target
	Mobile applications and smart sensors/
solutions 
	- 
	Mobile Applications Number

Smart sensors/
Solutions delivered/
installed: Number

Smart sensors/
solutions connected: Number
	Mobile Applications: 0

Smart sensors/
Solutions delivered/
installed: 0


Smart sensors/
solutions connected:0
	Mobile Applications:3


Smart sensors/
Solutions delivered/
installed: 
52 700

Smart sensors/
solutions connected:
45 000
	Q2
	2026
	Acceptance certificates for the three mobile applications (one application for the citizens for parking, one for parking enforcement officers, and one for waste collectors). The applications shall be downloadable as production ready application files from a website. 
52 700 smart sensors or solutions are delivered or installed to municipalities or the Deputy Ministry of Research Innovation and Digital Policy. 45 000 of these smart sensors or solutions shall be connected to the smart cities’ platform.

	178
	C3.4I6a
Regeneration and Revitalisation of Nicosia Inner City 
	Target
	Renovation of rooms in Nicosia. 
	- 
	Number
	0
	286
	Q2
	2026
	Taking-over reports issued by an Engineer or Architect for the private sector incentives scheme / taking-over certificates issued by an Engineer or Architect for the contracting Authority (Nicosia Municipality), certifying that renovation works have been carried out for at least 286 rooms in Nicosia.

	180
	C3.4R8
Efficiency of Justice
	Milestone
	Entry into force of new Rules of Civil Procedure
	Provision in new Rules of Civil Procedure (published in the Official Gazette) indicating the entry into force of the Rules of procedures (1 September 2023) 
	-
	-
	-
	Q3
	2023
	Entry into force of the new Rules of Civil Procedure for the new cases submitted to the court as from 1 September 2023. The new Rules of Civil Procedure shall modernise the hearing of cases in order to deliver a less costly, more accessible, and timelier service to parties. 

	181
	C3.4R8
Efficiency of Justice
	Target
	Reducing the backlog of cases and appeals
	-
	% (Percentage)
	0
	40
	Q2
	2024
	Reduction of the backlog of cases and appeals pending for over two years before the District Courts and the Supreme Court by 40% from the 31 December 2020 level of 16 740 pending civil cases and 2 139 pending civil and administrative appeals, as verified by an Annual Progress Report of the Action Plan to reduce backlog. 

	 183
	C3.4R9
Digital transformation of courts
	Milestone
	i-justice system
	Temporary acceptance certificate of Phase One of the i-justice system
	-
	-
	-
	Q2
	2026
	Issuance of the temporary acceptance certificate of Phase One of i-Justice System. This system shall be accessible through the court’s website. 


	185
	C3.4I7
Training of judges
	Milestone
	Training of judges 
	Trainings organised
	
	
	
	Q4
	2025
	Trainings for judges shall be organised on the revised Civil Procedure Rules and other judicial skills.

	186
	C3.4I8
Upgrading the infrastructure of courts
	Milestone
	Extension of the Famagusta District Court
	Project management team certifies the completion of the construction. 
	-
	-
	-
	Q4 
	2021
	Completion of construction of the extension to the Famagusta District Court building to support the operation of new courtrooms to try in addition to criminal also civil cases. 

	187
	C3.4R10
Improving the legal and institutional framework for fighting corruption
	Milestone
	Entry into force of the law establishing the Independent Authority against Corruption 
	Provision of the law indicating the entry into force of the law and start of operation of the Independent Authority against Corruption with key management positions filled and staff recruited. 
	-
	-
	-
	Q1 
	2022
	The Independent Authority against Corruption has been established on the basis of the entry into force of the corresponding law and is operational. The Authority shall coordinate the efforts of all bodies engaged in the fight against and prevention of corruption and shall supervise the timely implementation of actions by the different competent services. 

	188
	C3.4R10
Improving the legal and institutional framework for fighting corruption
	Milestone
	Entry into force of the law on Transparency in Decision-Making and Related Matters
	Provision of the law indicating the entry into force of the law
	-
	-
	-
	Q4 
	2021
	Entry into force of the law on Transparency in Decision-Making and Related Matters, including provisions to prevent conflict of interest. The law shall create the obligation to publicise contacts made between persons interested in being involved in public decision-making procedures and officials or members of the State service or of the wider public sector or with employees for the benefit of officials who, by their very position, have competence or possibility of initiating such procedures or formulating their content or contributing or determining the final outcome of such procedures. Information on such a contact, as well as its content and purposes, shall be officially recorded and be publicly available.

	189
	C3.4R10
Improving the legal and institutional framework for fighting corruption
	Milestone
	Entry into force of the law to protect whistle-blowers
	Provision of the law indicating the entry into force of the law
	-
	-
	-
	Q4 
	2021
	Entry into force of a law to protect whistle-blowers reporting fraud and corruption from internal sanctions. The law shall include supplementary provisions on the protection of persons reporting acts of corruption both in the public and the private sectors (whistle-blowers, persons not involved in the acts), further to the protection already provided for in the Protection of Witnesses Law 95(I)/2001. The law shall also provide measures of leniency for those who are involved in acts of corruption but voluntarily report to the police and/or offer cooperation with the authorities resulting in the full investigation and prosecution of the case.
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I. COMPONENT 3.5: SAFEGUARDING FISCAL AND FINANCIAL STABILITY
This component of the Cypriot recovery and resilience plan addresses the challenges of fiscal and financial vulnerabilities, including macroeconomic imbalances related thereto. The aim is to safeguard financial stability by reducing legacy risks in the banking sector, putting in place measures against high private indebtedness, and for the supervision in the non-bank sector. To ensure fiscal stability, Cyprus aims at combating tax evasion, tax avoidance and aggressive tax planning; and providing policy makers with comprehensive data in order to design a fair tax system. The envisaged measures are expected to make revenue collection more efficient and Cyprus’ tax system fairer, reducing the spill-over effects from aggressive tax planning. 
The component supports addressing the Country-Specific Recommendations on financial stability and private indebtedness (Country-Specific Recommendations 2 and 5 of 2019), and on addressing features of the tax system that facilitate aggressive tax planning by individuals and multinationals (Country-Specific Recommendation 4 of 2020 and Country-Specific Recommendation 1 of 2019). 
 
I.1. 	Description of the reforms and investments for non-repayable financial support
Safeguarding financial stability
Reform 11 (C3.5R11): Legal framework for a National Sanctions Implementation Unit
The objective of this reform is to reinforce oversight in the banking and non-banking financial sectors. 
The reform consists of the entry into force of legal act(s) on establishing the legal framework for a National Sanctions Implementation Unit. 
 
Reform 2 (C3.5R2): Framework and Action Plan for addressing non-performing loans 
The objective of the measure is to address financial risks related to legacy non-performing loans in the banking sector by continuing efforts to improve the asset quality of banks and strengthening the working environment for servicing of loans.
The reform shall consist in (i) implementing an action plan to address the remaining stock of legacy non-performing loans and (ii) adopting a package of three amending laws regarding credit acquiring companies and servicers (placing of loan servicers under regulation and supervision by the Central Bank; granting access for loan servicers and credit acquiring companies to the Land Registry; and aligning notification requirements in case of purchase of a loan by a credit acquiring company). A progress report on the action plan shall be prepared by 30 June 2023 and approved by the Council of Ministers, tracking the reduction of non-performing loans in the banking sector towards the indicative reference values of 6% gross and 3% net non-performing loans ratio and proposing policy measures where appropriate.
The implementation of the reform shall be completed by 30 June 2023. 
 
Reform 3 (C3.5R3): Strategy for addressing inadequacies of the property transaction system (title deeds) 
The objective of the reform is to address inefficiencies in the system of issuing and transferring title deeds, which results in property rights not being defined, complicates foreclosure procedures and hinders the liquidation of collateral. 
The reform shall consist in: (i) examination of pending cases for the issuance of title deeds or rejection of the cases, (ii) extension of the new planning and building permit policy, currently up to two residential units, to four residential units in a plot, which shall reduce the time needed to issue building and spatial permits, (iii) review of the Streets and Buildings Law to introduce the right incentives for the supervising engineer to further discourage irregularities that would result in title deeds not being issued, (iv) amendment of the Sale of Property (Specific Performance) Law, which shall ensure in advance that the transfer of immovable property is executed as soon as the buyer fulfils his/her contractual obligations.
The implementation of the reform shall be completed by 31 December 2023. 
 
Reform 4 (C3.5R4): Digital system for the exchange of data and the provision of credit scoring services
The objective of this reform is to fight high private indebtedness. 
This measure consists in (i) the entry into force of legal act(s) on the ARTEMIS data exchange mechanism and (ii) the ARTEMIS data exchange mechanism in User Acceptance Testing phase.
 
Reform 5 (C3.5R5): Framework for Management of Private Debt 
The objective of this reform is to prevent and manage the stock of private debt. 
The measure consists of (a) an Action Plan on liabilities monitoring (LMR) and (b) the entry into force of legal act(s) for the management of private debt. 
 
Reform 6 (C3.5R6): Reinforcing the insolvency framework 
The objective of this reform is to reinforce the insolvency framework, and the functioning of the Department of Insolvency.
This measure consists in (i) adopting the legal and institutional framework for insolvency and (ii) accessible digital systems of the Department of Insolvency. 
 
Reform 7 (C3.5R7): Strategy for Combating Financial Illiteracy 
The objective of the measure is to promote financial literacy. It aims at enhancing financial education within the general population, improve financial decision making, correct wrong attitudes and biases, support more informed and financially responsible citizens and ultimately, help improve debt repayment discipline.
The reform shall consist in preparing a strategy for combating financial illiteracy by: (i) identifying the issues of financial illiteracy (ii) reviewing the international literature on the topic, and (iii) providing an action plan for implementation. 
The implementation of the reform shall be completed by 31 December 2023.
 
Reform 8 (C3.5R8): Enhancing supervision of Insurance and Pension Funds 
The objective of this reform is to enhance the supervision of the insurance and pension funds.
This measure consists in (i) the employment of additional permanent employees of the supervisory authorities, (ii) preparing and implementing tools and actions in line with the regulatory frameworks. 
 
Investment 1 (C3.5I1): Enhancement of the Supervisory Function of Cyprus Securities and Exchange Commission
The objective of the measure is to enhance the supervisory capacity of Cyprus Securities and Exchange Commission (CySec) through digitalisation – allowing for better supervision of transactions. 
The investment shall consist in developing an advanced digital system, based on cloud architecture, covering the supervision needs of European Market Infrastructure Regulation (EMIR)and the Securities Financing Transactions Regulation (SFTR). The new system shall support the following features: (i) connect to the European Securities and Markets Authority (ESMA) hub; load and pre-process transaction data, (ii) aggregate and perform queries on data to generate regulatory insights (iii) generate on-schedule and ad-hoc reports.
The implementation of the investment shall be completed by 31 December 2023.
 
Safeguarding fiscal stability
Reform 9 (C3.5R9): Digitalising tax collection
The objective of this reform is to make tax collection more efficient. 
This measure consists in an IT system as a single point for taxpayer services.
 
Reform 10 (C3.5R10): Addressing Aggressive Tax Planning
The objective of this reform is to combat tax evasion and aggressive tax planning by Multinational Enterprises. 
This measure consists in the entry into force of legal act(s) to address aggressive tax planning. 
 
Investment 2 (C3.5I2): Modernisation of Customs and Electronic Payment System
The objective of this investment is to simplify customs formalities and reduce the administrative cost for stakeholders. 
This measure consists in information systems or functionalities, for which acceptance certificates have been issued. 
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I.2. 	Milestones, targets, indicators, and timetable for monitoring and implementation for non-repayable financial support
	Sequential Number
	Related Measure (Reform or Investment)
	Milestone/Target
	Name
	Qualitative indicators 
(for milestones)
	Quantitative indicators 
(for targets)
	Indicative timeline for completion
	Description of each milestone and target

	
	
	
	
	
	Unit of measure
	Baseline
	Goal
	Quarter
	Year
	

	191a
	C3.5R11
Legal framework for a National Sanctions Implementation Unit 
	Milestone
	Legal framework for a National Sanctions Implementation Unit 
	Entry into force of the legal act(s)
	
	
	
	Q4
	2025
	Entry into force of legal act(s) establishing the legal framework for a National Sanctions Implementation Unit.

	192
	C3.5R2 Framework and Action Plan for addressing NPLs
	Milestone
	Entry into force of the package of amending laws regarding credit acquiring companies (CAC) and credit servicers to improve the working environment for non-performing loans management
	Provision in the law indicating the entry into force of the respective laws
	-
	-
	-
	Q4
	2021
	Entry into force of the following three laws: 
(a) The Credit Facilities Purchase and Related Matters (Amending) Law of 2021, which shall put non-performing loan servicers under regulation and supervision by the Central Bank; 
(b) The Immovable Property (Transfer, Registration and Valuation) (Amending) Law of 2021, which shall give access for non-performing loan servicers and credit acquiring companies to the Land Registry 
(c) Evidence (Amending) Law 2020, which shall align notification requirements in case of purchase of a loan by a credit acquiring company.

	193
	C3.5R3 
Strategy for addressing inadequacies of the property transaction system (title deeds)
	Target
	Reduction of backlog of cases for issuance of title deed either by issuing title deeds or by rejecting the case
	-
	% (Percentage)
	0
	80
	Q2
	2023
	Reduction of backlog of pending cases for issuance of title deeds either by issuing title deeds (the legal document constituting the evidence of a right to the ownership of a property) or by rejecting the case. Title deeds for 1 050 developments are pending for assessment, corresponding to 20 000 title deeds. Of this total of 20 000 pending title deeds, 80% shall be resolved resulting either to the issuance of title deeds or to a rejection of the case.

	194
	C3.5R3
Strategy for addressing inadequacies of the property transaction system (title deeds)
	Milestone
	Extension of the New Planning and Building Permit Policy 
	Decree issued by the Minister of Interior
	-


	-
	-
	Q4
	2022
	Extension of the New Planning and Building Permit Policy for up to four residential units in residential plots. The Policy provides the possibility to submit applications electronically and introduces fixed deadlines to grant planning and building permits (ten to twenty days). 

	195
	C3.5R3 
Strategy for addressing inadequacies of the property transaction system (title deeds)
	Milestone
	Entry into force of the amendment of the Sale of Property (Specific Performance) Law 
	Provision in the law indicating the entry into force of the amended Sale of Property (Specific Performance) Law
	-
	-
	-
	Q4
	2022
	Entry into force of the amended Sale of Property (Specific Performance) Law to safeguard the buyers interests in advance. The amendment shall allow for transfer of Title Deeds, under full safety and legal certainty, while minimizing operational costs and delays through checks at a preliminary stage to identify specific obstacles to the transfer before the payment of the purchase price. The aim is to create a mechanism to safeguard the interests of the buyers of immovable property and ensure in advance that the transfer of immovable property shall be executed as soon as the buyer fulfils his/her contractual obligations.

	196
	C3.5R3 
Strategy for addressing inadequacies of the property transaction system (title deeds)
	Milestone
	Review of the Streets and Building Law 
	Provision in the law indicating the entry into force of the amended Streets and Building Law
	-
	-
	-
	Q4
	2023
	Entry into force of the Streets and Building Law which shall introduce the right incentives for the supervising engineer to (i) oversee the project development in accordance with the permit issued, to further discourage irregularities that would result in title deeds not being issued and (ii) submit to the competent authority a certificate confirming the completion of work in line with the permit issued.

	197
	C3.5R4 
New legal framework and system of exchange of data and credit bureau
	Milestone
	Entry into force of the framework and system of exchange of data legislation
	Provision in the legislation indicating the entry into force of the legislation
	-
	-
	-
	Q1
	2023
	Entry into force of the legislation on the framework and system of exchange of data by ARTEMIS credit bureau, which shall eliminate impediments in the current framework so as to allow it to provide credit scoring services. The main elements of the amendment shall be to broaden the supervisory role of the Central Bank of Cyprus, to maintain a duty to collect data for credit facilities by credit institutions and other creditors, to provide Insolvency Department data, and to define the terms and conditions of access to data and its protection.

	198
	C3.5R4 
Digital system for the exchange of data and the provision of credit scoring services
	Milestone
	 Entry into force of legal act(s) on the ARTEMIS data exchange mechanism and ARTEMIS data exchange mechanism providing credit scoring services in User Acceptance Testing phase
	Entry into force of legal act(s); digital system in User Acceptance Testing phase
	-
	-
	-
	Q4
	2024
	Entry into force of legal act(s), which shall: 
I. Include credit scoring services
II. Specify the data to be submitted and the procedure for submitting data to the ARTEMIS data exchange mechanism
III. Mandate the production of credit scoring.
Furthermore, the ARTEMIS data exchange mechanism in User Acceptance Testing (UAT) phase shall demonstrate the capacity to provide credit scoring services.

	199
	C3.5R5 
Action plan for the development of a liability monitoring register
	Milestone
	Action Plan for the development of a liability monitoring register 
	Approval of the Action Plan by the Council of Ministers
	-
	-
	-
	Q4
	2022
	The Action Plan shall put forward the necessary steps for introducing the liability monitor register that shall: 
- utilise an electronic database, collecting data on liabilities from various public and private creditors, such as the credit registry under reform C3.5R4. 
- enable the design and implementation of targeted policies for preventing and managing private indebtedness.

	200
	C3.5R5 
Framework for Management of Private Debt
	Milestone
	Entry into force of legal act(s) for the management of private debt. 
	Entry into force of the legal act(s)
	
	
	
	Q4
	2024
	Entry into force of legal act(s) for the management of private debt.

	201
	C3.5R6 Reinforcing and strengthening the insolvency framework
	Milestone
	Full implementation and full operation of the legal and institutional framework for insolvency 
	Appointment of staff confirmed by the Official Gazette. Council of Ministers’ approval of the Progress Report 
	-
	-
	-
	Q4
	2022
	Full implementation and full operation of the legal and institutional framework on insolvency through: (a) appointment of staff for all levels of the organisational structure of the Department of Insolvency, and delivery of trainings for the personnel, (b) establishment of a communication plan for promoting insolvency proceedings, (c) approval of a customer service line, (d) establishment of a framework for continuous professional development for insolvency Practitioners. 

	202
	C3.5R6 Reinforcing the insolvency framework
	Milestone
	Digital systems of the Department of Insolvency accessible 
	Digital system accessible 
	-
	-
	-
	Q2
	2025
	The digital systems of the Department of Insolvency shall be accessible.

	203
	C3.5R7 
Strategy for Combating Financial Illiteracy
	Milestone
	Strategy for Combating Financial Illiteracy
	Approval of the Strategy for Combating Financial Illiteracy by the Council of Ministers
	-
	-
	-
	Q4
	2023
	The Strategy for Combating Financial Illiteracy shall outline its goal and objectives, specify the channels for promoting financial literacy, and include specific actions for implementation. The reform shall also include completion of initiatives promoting financial literacy. 

	204
	C3.5R8 Enhancing supervision of Insurance and Pension Funds
	Target
	Employment of additional permanent employees of the Registrar of Occupational Retirement Benefits Fund (RORBF) and the Insurance Companies Control Service (ICCS) 
	-
	Number
	0
	16
	Q2
	2026
	Employment (placing or seconding or transferring) of thirteen additional permanent employees for the Registrar of Occupational Retirement Benefit Funds (RORBF) and three additional permanent employees for the Insurance Companies Control Service (ICCS). 

	205
	C3.5R8 Enhancing supervision of Insurance and Pension Funds
	Milestone
	Supervisory tools including data collection and analysis tool
	Support tools for enhancing the supervision of pension funds and insurance companies 
	-
	-
	-
	Q4
	2023
	 Implementation of tools (for example, procedures, checklists, fitness and propriety applications) in line with new legislation (providing for the establishment, activities and supervision of Institutions for Occupational Retirement Benefits Law of 2020 -L 10(I)/2020 and the legislation of the Insurance and Reinsurance Business and Other Related Issues Law of 2016 (Ν.38(Ι)/2016.

	206
	C3.5I1 Enhancement of the Supervisory Function of the Cyprus Securities and Exchange Commission
	Milestone
	Digital system for supervision of transactions for the Cyprus Securities and Exchange Commission 
	Project management committee verifies acceptance of deliverables in due time; and quality and standards as specified in tender documents

	-
	-
	-
	Q4
	2023
	Implementation of a new digital system of supervision of transactions. The new digital system shall have the following features: 
- Loading and pre-processing of Transaction data. 
- Aggregations and queries on data to generate regulatory insights. 
- Generation of on-schedule and ad-hoc reports.

	207a
	C3.5R9 Improving tax collection and effectiveness of the Tax Department
	Milestone
	Operation of VAT Services within an Integrated Tax Administration System (ITAS)
	Project Board Approval of the Project Deliverables for completion, installation, and operation of a new integrated VAT System 
	-
	-
	-
	Q1
	2022
	The Cyprus Tax Department (CTD) shall put into operation an Integrated Tax Administration System (ITAS) that shall support the tax administration functionalities and processes. The functionalities related to the VAT Services shall be completed and operational within this system.

	207b
	C3.5R9 Improving tax collection and effectiveness of the Tax Department
	Milestone
	Purchase of the new building for the integrated Nicosia District Office and Large Taxpayers’ Office
	Completion of the purchase and start of operations
	
	
	
	Q3
	2023
	The new building for the integrated Nicosia District Office and Large Taxpayers’ Office has been purchased. 

	208
	C3.5R9 Digitalising tax collection 
	Milestone
	Direct tax administration services of the Tax department within the ITAS
	Direct Taxes are ready to be put into productive operation within ITAS and have been approved by the board
	-
	-
	-
	Q1
	2026

	The Tax administration services for the following Direct Taxes are ready to be put into productive operation within ITAS and have been approved by the board:
· Income Tax withheld at source by employers (PAYE),
· Defence Tax
· Submission Services for the Summary Information Table for Controlled Transactions

Together with the following horizontal functionalities:
· Online Registration to the Tax Registry of the Department 
· Tax Audit Operation Services,
· Objections Services,
· Cy Login Authentication Functionality,
· Appeals Services.


	209
	C3.5R10 Addressing Aggressive Tax Planning
	Milestone
	Entry into force of the law to tackle aggressive tax planning 
	Provision in the law indicating the entry into force of the law 
	-
	-
	-
	Q4
	2022
	Entry into force of a law to tackle aggressive tax planning by (a) imposing a withholding tax on interest, dividends and royalty payments to jurisdictions included in Annex I of the Council conclusions on the revised EU list of non-cooperative jurisdictions for tax purposes and (b) introduction of a further corporate tax residency test based on the incorporation of each entity. 

	210
	C3.5R10 Addressing Aggressive Tax Planning
	Milestone
	Entry into force of legal act(s) to tackle aggressive tax planning 
	Entry into force of legal act(s) 
	-
	-
	-
	Q4
	2024
	Entry into force of legal act(s) to introduce withholding tax on dividend payments to low tax jurisdictions and applying non-deductibility on interest and royalty payments to low tax jurisdictions. 

	211
	C3.5R10 Addressing Aggressive Tax Planning
	Milestone
	Entry into force of legal act(s) addressing aggressive tax planning 
	Entry into force of legal act(s) 
	-
	-
	-
	Q2
	2026
	A study shall assess the tax framework with respect to measures related to aggressive tax planning. Legal act(s) addressing aggressive tax planning based on the findings of this study shall enter into force.

	212
	C3.5I2 Modernisation of Customs and Electronic Payment System 
	Target
	Putting into operation the information systems– envisaged under the Union Customs Code (UCC)
	-
	Number
	0
	2
	Q4
	2023
	At least two of the following import-related information systems have been completed, installed, and put into operation: 
1. Automated Export System 
2. New Computerised Transit System
3. EU Single Window 
4. Union Customs Code 
5. Guarantee Management
6. Union Customs Code 
7. SURVEILLANCE 3 
8. Union Customs Code - Import Control System 2 
9. Import Applications under the Union Customs Code 
10. Customs Union Performance – Management Information System 
11. Union Customs Code Proof of Union Status 
12. Uniform User Management and Digital Signature


	213
	C3.5I2 Modernisation of Customs and Electronic Payment System 
	Target
	Information systems or functionalities
	-
	Number
	2
	11
	Q4
	2025
	Acceptance Certificates shall be issued on the following:
1. New Computerised Transit System
2. EU Single Window
3. Automated Import System (AIS)
4. The Union Customs Code – Special Procedures for Import and Export
5. SURVEILLANCE 3
6. Centralized Clearance for Import Applications under the Union Customs Code
7. Customs Union Performance – Management Information System
8. Union Customs Code Proof of Union Status
9. The Uniform User Management and Digital Signature system
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J. COMPONENT 4.1: Upgrade infrastructure for connectivity
This component of the Cypriot recovery and resilience plan contributes to addressing infrastructure challenges in the area of data connectivity, in particular in rural areas, with a view to narrowing the rural-urban divide, as well as differences along gender, age, income and education. 
The objective of the component is to enhance access to communication infrastructure for all citizens, thus bridging the digital divide and supporting an inclusive digital transformation. 
The component addresses the country-specific recommendation on investment in the digital transition and the digitalisation (Country-Specific Recommendation 4 of 2019 and Country-Specific Recommendation 3 of 2020). 
No measure in this component does significant harm to environmental objectives within the meaning of Article 17 of Regulation (EU) 2020/852, taking into account the description of the measures and the mitigating steps set out in the recovery and resilience plan in accordance with the DNSH Technical Guidance (2021/C58/01).

J.1. 	Description of the reforms and investments for non-repayable financial support
Reform 1 (C4.1R1): Empower the National Regulatory Authority (OCECPR)
The objective of this reform is to facilitate broadband connectivity in Cyprus.
This measure consists in enabling the Office of the Commissioner of Electronic Communications and Postal Regulation (OCECPR) to collect and publish geographical data on electronic communication networks. 

Reform 2 (C4.1R2): Simplification of the administrative procedures for the deployment of VHCN 
The objective of this reform is to facilitate the build-up of Very High Capacity Networks (VHCN) infrastructure.
The reform consists in the entry into force of administrative acts for the deployment of very high capacity networks.

Investment 1 (C4.1I1): Expansion of Very High-Capacity Networks in underserved areas
The objective of this investment is to expand VHCN, addressing territorial disparities of broadband availability. 
This measure consists in supporting investment in VHCN in areas of no interest to private investors.

Investment 2 (C4.1I2): Upgrade internet connection to be “Gigabit-ready” and support connectivity take-up
The objective of this investment is to encourage the widespread take-up of VHCN.
This measure consists in vouchers for higher capacity internet connections. 
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J.2. 	Milestones, targets, indicators, and timetable for monitoring and implementation for non-repayable financial support
	Sequential Number
	Related
Measure
(Reform or Investment)
	Milestone/Target
	Name
	Qualitative indicators 
(for milestones)
	Quantitative indicators 
(for targets)
	Indicative timeline for completion
	Description of each milestone and target

	
	
	
	
	
	Unit of measure
	Baseline
	Goal
	Quarter
	Year
	

	214
	C4.1R1
Empower the National Regulatory Authority (OCECPR)
	Milestone
	Launch of the geographical survey and entry into force of secondary legislation 
	Entry into force of the secondary legislation and launch of the survey
	-
	-
	-
	Q1
	2022
	The secondary legislation shall enter into force and cover the main aspects related to the survey such as the type, the degree of analysis and the form of the required information, as well as the persons from whom the required information is requested.
Launch of the geographical survey of the reach of electronic networks capable of delivering broadband networks and physical infrastructures based on Article 22 of the European Electronic Communications Code.

	215
	C4.1R1
Empower the National Regulatory Authority (OCECPR)
	Milestone
	Web portal on broadband and infrastructure mapping
	The web portal is accessible 
	-
	-
	-
	Q4
	2024
	The web portal on broadband and infrastructure mapping is accessible.

	216
	C4.1R2
Simplification of the administrative procedures for the deployment of VHCN 
	Milestone
	Entry into force of the administrative acts for very high capacity networks’ deployment
	Provision in the administrative acts indicating the entry into force of the respective acts
	-
	-
	-
	Q2
	2024
	Entry into force of administrative acts for the reduction of administrative barriers for the deployment of very high capacity networks, which may include, but not be limited to, acts facilitating permit granting procedures or access to physical infrastructure.

	217
	C4.1I1
Expansion of very high capacity Networks in underserved areas
	Milestone
	Start of very high capacity networks’ deployment in underserved areas
	Signed contracts with contractors to deploy very high capacity networks in areas of no interest to private very high capacity network investors
	-
	-
	-
	Q4
	2023
	Contracts have been signed with contractors, which shall have been selected through an open tender procedure, to deploy very high capacity networks (in particular, fixed or mobile (5G) networks offering a download speed of at least 100Mbps, which shall be readily upgradable to Gigabit for fixed access) in areas of no interest to private very high capacity network investors.

	219
	C4.1I1
Expansion of very high capacity Networks in underserved areas
	Milestone
	Very high capacity networks are accessible in areas of no interest to private investors
	Three acceptance certificates (one per lot) issued by the contracting authority
	
	0
	
	Q4
	2025
	At least three areas (lots) as defined in contracts under milestone 217 are covered by very high capacity networks.

	220
	C4.1I2
Upgrade internet connection to be “Gigabit-ready” and promote connectivity take-up 
	Target
	Expansion of Gigabit-ready internet connection take-up by households
	-
	Number
	0
	24 300
	Q2
	2023
	Internet connection has been upgraded to be able to support provision of Gigabit connectivity in at least 24 300 homes.

	221
	C4.1I2
Upgrade internet connection to be “Gigabit-ready” and support connectivity take-up
	Target
	Gigabit-ready internet connection take-up by at least 82 000 households
	-
	Number
	24 300
	82 000
	Q2
	2025
	Internet connection has been upgraded to be able to support provision of gigabit connectivity in at least 82 000 households.
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K. COMPONENT 4.2: PROMOTE E-GOVERNMENT
This component of the Cypriot recovery and resilience plan contributes to accelerating the digital transformation of Cyprus through the digitalisation of government services enhancing the efficiency and the provision of online, secure, and prompt services to citizens, in a user friendly, efficient, and effective way. This is expected to facilitate the interaction between citizens and the public services, without the need for physical presence.
The objective of the component is to build a secured, integrated, and modern digital architecture to achieve the transformation to a digital government. 
The component addresses the country-specific recommendation on investment in the digital transition and the digitalisation (Country-Specific Recommendation 4 of 2019 and Country-Specific Recommendation 3 of 2020).

K.1. 	Description of the reforms and investments for non-repayable financial support
Reform 1 (C4.2R1): Digital Services Factory (DSF)
The objective of this reform is to facilitate the interaction with public services.
This measure consists in designing a Service Delivery Model for the provision of digital services to the public.

Reform 2 (C4.2R2): New cloud policy with regard to government IT systems and services and infrastructure set-up
The objective of this measure is to elaborate the cloud policy of the government.
This measure consists in two data centres providing hosting services to government IT systems, and the adoption of a national cloud policy. 

Reform 3 (C4.2R3): Police procedures digitalisation (Digipol)
The objective of this reform is to digitalise procedures for the Cyprus Police. 
This measure consists in a platform (Digipol) of demands for police procedures and services. 

Reform 4 (C4.2R4): Setting up the beneficial ownership registry
The objective of the measure is to set up the register for the submission of the data of beneficial owners of all corporate and other legal entities. Such registration aims to improve corporate trust and transparency in Cyprus and shall make it clear who ultimately owns and controls companies and other legal entities. 
The reform shall consist in setting up the register. Currently, an online platform has been developed as an interim solution but its functionalities are limited. The reform shall result in a solution with the necessary functionalities to support the maintenance of the register and management of relevant information (for example by sending out notifications for updating, enforcement of late filing fees, search facilities with prescribed levels of access). This aims to support the registration of the data of beneficial owners of all corporate and other legal entities and achieve interconnection with the beneficial ownership registers of other Member States.
The implementation of the reform shall be completed by 31 December 2023.

Investment 1 (C4.2I1): Digitalisation of central government ministries or departments
The objective of this investment is to digitalise workflows in a number of central government ministries or departments.
This measure consists in digitalisation projects in five central government ministries or departments. 

Investment 2 (C4.2I2): Digitalisation of the Cyprus Ports Authority
The objective of this investment is to support digital infrastructure and processes of the Cyprus Ports Authority (CPA).
The measure consists in investing in information technology equipment and systems for CPA. 
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K.2. 	Milestones, targets, indicators, and timetable for monitoring and implementation for non-repayable financial support
	Sequential Number
	Related Measure (Reform or Investment)
	Milestone/ Target
	Name
	Qualitative indicators 
(for milestones)
	Quantitative indicators 
(for targets)
	Timeline for completion 
(indicate the quarter and the year)
	Description and clear definition of each milestone and target

	
	
	
	
	
	Unit of measure
	Baseline
	Goal
	Quarter
	Year
	

	224
	C4.2R1
Digital Services Factory
	Milestone
	Definition of the Service Delivery Model for the Digital Services Factory 
	Appointment decision of the Deputy Minister of Research, Innovation and Digital Policy establishing the team; publication of the standards on the website of the Deputy Ministry 
	-
	-
	-
	Q4
	2022
	The Service Delivery Model for the Digital Services Factory has been defined so as to enable the efficient provision of high-quality and user-friendly digital services to the public. This shall include: (a) the establishment of the core Digital Services Factory team (including the procurement of services of experts from the private sector), and (b) definition of the standards and procedures for the development of digital services. 

	225
	C4.2R1
Digital Services Factory
	Target
	Expansion of delivery of government services online through the Digital Services Factory
	-
	Number
	0
	20
	Q4
	2023
	Digitalisation and delivery online of at least 20 services to the public through the Digital Services Factory, using the defined Service Delivery Model (under milestone with a sequential number 224) and agile methodologies.

	226
	C4.2R1
Digital Services Factory
	Target
	At least 70 services through the Digital Services Factory
	-
	Number
	20
	70
	Q2
	2026
	Digitalisation of at least 70 services through the Digital Services Factory.

	227
	C4.2R2
New cloud policy with regard to government IT systems and services and infrastructure set-up
	Target
	Two data centres with hosting services
	-
	Number
	0
	2
	Q4
	2024
	Two data centres with hosting services for government IT systems.

	228
	C4.2R2
New cloud policy with regard to government IT systems and services and infrastructure set-up
	Milestone 
	Adoption of a national cloud policy by the Council of Ministers
	National cloud policy adopted by the Council of Ministers
	
	
	
	Q4
	2025
	A National Cloud Policy on the use of cloud computing technologies in the public sector is adopted by the Council of Ministers.

	229
	C4.2R3
Police Procedures digitalisation Digipol
	Milestone
	Digipol prototype operational 
	Declaration by Cyprus Police confirming that the prototype platform (Digipol) is operational
	-
	-
	-
	Q2
	2023
	The prototype platform (Digipol) is operational. Police officers shall be the users and have access to the prototype Digipol for familiarity and training purposes. 

	230
	C4.2R3
Police Procedures digitalisation (Digipol)
	Milestone
	Digipol accessible
	-
	
	
	
	Q3
	2025
	Digipol shall be accessible. Training and dissemination activities have been conducted. 

	231
	C4.2R4
Setting up the beneficial ownership registry
	Milestone
	Beneficial ownership registry available for use 
	Beneficial ownership registry publicly available online at national and European Level
	-
	-
	-
	Q4
	2023
	The beneficial ownership registry shall be deployed and become available for use at national level and European level, enabling users to check the ultimate beneficial ownership information of legal entities and to achieve interconnection of the beneficiary ownership registers with other Member States.

	232
	C4.2I1
Digitalisation in various Central Government Ministries - Services
	Milestone
	Repository system for audit and control: information for monitoring implementation of RRF
	An audit report confirming repository system functionalities
	-
	-
	-
	Q1
	2022
	A repository system for monitoring the implementation of the RRF shall be in place and operational. The system shall include, as a minimum, the following functionalities:
(1) collection of data and monitoring of the achievement of milestones and targets; (2) collect, store, and ensure access to the data required by Article 22(2)(d) (i) to (iii) of Regulation (EU) 2021/241.

	233
	C4.2I1
Digitalisation in various Central Government Ministries - Services
	Target
	Start of the digital upgrade of a number of central government ministries and departments
	-
	Number
	0
	4
	Q1
	2022
	The contracts with providers selected through public procurement procedures have been signed to digitalise/digitally upgrade at least four of the following central government ministries/departments: 
1. Road Transport Department of the Ministry of Transport, Communication and Works, 
2. Deputy Ministry of Shipping. 
3. Ministry of Foreign Affairs 
4. Directorate General Growth 
5. Department of Town Planning and Housing of the Ministry of Interior (for Architectural Heritage).

	235
	C4.2I1
Digitalisation of Central Government Ministries or departments
	Target
	Delivery of digital systems of five central government ministries or departments
	-
	Number
	0
	5
	Q4
	2025
	[bookmark: _Hlk213779827]Implementation Completion Reports or Acceptance Certificates have been issued for digital systems for the five central government ministries or departments from the list in target with sequential number 233. For the Department of Road Transport, the system shall include the digitalisation of workflows that may include, but it is not limited to, Vehicle registration, Road tax license renewal and vehicle inspection. For the Deputy Ministry of Shipping, it may include, but it is not limited to, Issuance or Renewal of Endorsements and Seamen’s Books, Ship registration, and the Electronic Tonnage Tax System.

	236
	C4.2I2
Digitalisation of the Cyprus Ports Authority
	Target
	Start of the digital upgrade of the Cyprus Ports Authority
	-
	Number
	0
	4
	Q2
	2023
	The contracts with providers selected through a public procurement procedure have been signed to develop/upgrade at least four of the following seven systems for the Cyprus Ports Authority: 
1. Upgrade of the Port Community System; 
2. Installation of VTS Station; 
3. Digitisation of CPA archives; 
4. Upgrade of IT infrastructure (such as network, switches); 
5. Update IS systems; 
6. Installation of an HR Management System; 
7. Upgrade CPA Servers; 
 
and contracts have been signed to develop the following e-service: 
 
• monitoring and safety of navigation to and from the ports of Larnaca and Vasiliko.

	237
	C4.2I2
Digitalisation of the Cyprus Ports Authority
	Target
	IT infrastructure of Cyprus Ports Authority
	-
	Number
	0
	4
	Q2
	2024
	The following infrastructure and systems are delivered:
1. VTS Station; 
2. IT infrastructure (structured cabling and ethernet switches); 
3.Solutions or services for the security of information systems (IS); 
4. CPA servers. 

	238
	C4.2I2
Digitalisation of the Cyprus Ports Authority
	Target
	IT infrastructure of Cyprus Ports Authority
	-
	Number
	4
	7
	Q4
	2025
	The following infrastructure, systems and services are delivered: 
1. Upgrade of the Port Community System in a User Acceptance Testing (UAT) environment; 
2. Digitisation of CPA archives; 
3. HR Management System in a User Acceptance Testing (UAT) environment. 
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L. COMPONENT 5.1: EDUCATIONAL SYSTEM MODERNISATION, UPSKILLING AND RETRAINING 
This component of the Cypriot Recovery and Resilience plan addresses the challenges of low participation in vocational education and training (VET) and lifelong learning, rising skills mismatches (particularly among young graduates) and poor digital skills. It further addresses the quality of teaching and the availability and affordability of early childhood education and care (ECEC) for children aged four years old. Its objective is to (i) improve the quality and effectiveness of education and training at all levels, (ii) foster the uptake of labour market-relevant reskilling and upskilling opportunities, in particular regarding the twin transitions, across society regardless of employment status, skills level or age, and (iii) modernise the school structures making them fit for the digital transition.
The reforms and investments included in the component address the country-specific recommendations on education and skills (country-specific recommendation 2 2020 and country-specific recommendation 3 2019), early childhood education and care (country-specific recommendation 3 2019) as well as on digital skills (country-specific recommendation 4 2019 and country-specific recommendation 3 2020).
L.1. 	Description of the reforms and investments for non-repayable financial support
Reform 1 (C5.1R1): Addressing skills mismatch between education and labour market (Secondary and Higher Education)
The objective of this reform is to address the skills mismatch between the labour market and the secondary and higher education system. 
This measure consists in actions included in the National Action Plan.

Reform 2 (C5.1R2): A school evaluation system and formative evaluation of teachers
The objective of this reform is to enhance the quality of education and consequently students’ educational outcomes.
This measure consists in a school evaluation system and formative evaluation of teachers.

Reform 3 (C5.1R3): Gradual extension of free compulsory pre-primary education from the age of four 
The objective of this reform is to enhance the availability and affordability of early childhood education and care (ECEC).
This measure consists in the extension of free compulsory pre-primary education from the age of four. 

Reform 4 (C5.1R4): Digital transformation of school units with the aim of supporting digital skills and skills related to STEM education
The objective of this reform is to support the digital transition of the education system.
This measure consists in the supply or financial support for digital equipment to schools and students.

Reform 5 (C5.1R5): E-skills Action Plan – Delivery of specific actions
This objective of this reform is to enhance digital competences across population groups. 
This measure consists in actions related to the E-skills action plan.

Investment 1(C5.1I1): Construction of one Model Technical School
The objective of this investment is to extend the capacity of vocational education and training (VET) in Cyprus. 
This measure consists in the signature of the contract for the construction of one new technical school in Limassol 

Investment 2 (C5.1I2): Skilling, Reskilling and Upskilling
The objective of this investment is to support the skills of the population.
This measure consists in training participants in programmes for digital, green, blue, and entrepreneurial skills.
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L.2. Milestones, targets, indicators, and timetable for monitoring and implementation for non-repayable financial support
	Sequential Number
	Related Measure (Reform or Investment)
	Milestone / Target
	Name
	Qualitative indicators 
(for milestones)
	Quantitative indicators 
(for targets)
	Indicative timeline for completion
	Description of each milestone and target

	
	
	
	
	
	Unit of measure
	Baseline
	Goal
	Quarter
	Year
	

	239a
	C5.1R1
Addressing skills mismatch between education and labour market (Secondary and Higher Education)
	Milestone
	Measures included in the National Action Plan 
	Publication of report and approval of the curricula and programmes by competent authorities
	-
	-
	-
	Q4
	2024
	The milestone consists in the following:
(a) the preliminary results of a “Graduate Tracking of Cyprus Higher Education" survey and a published report on the survey.
(b) 40 educational curricula in secondary schools are amended to support the following skills that may include but it is not limited to soft, hard, entrepreneurial skills 
(c) two new programmes of study in secondary general, and vocational education and training, 

	239b
	C5.1R1
Addressing skills mismatch between education and labour market (Secondary and Higher Education)
	Target
	In-job shadowing programme 
	
	Number
	0
	2 250
	Q2
	2026
	In-job shadowing programme for at least 2 250 secondary general education pupils.

	239c
	C5.1R1
Addressing skills mismatch between education and labour market (Secondary and Higher Education)
	Target
	Laboratories equipped 
	-
	Number
	0
	170
	Q2
	2026
	Acceptance certificate(s) for the delivery of laboratory equipment to 170 school laboratories of the Directorate of Secondary General Education of the Cyprus Ministry of Education, Sport and Youth.

	241
	C5.1R2
A school evaluation system and formative evaluation of teachers
	Milestone
	Council of Ministers Decision for a new School Evaluation system and entry into force of the legal act(s) for the Formative Evaluation of Teachers
	Entry into force of the legal act(s) 
	-
	-
	-
	Q2
	2025
	Council of Ministers Decision for a new School Evaluation system and entry into force of the legal act(s) concerning the formative evaluation of teachers and the establishment of Committee(s).

	243
	C5.1R3
Gradual extension of free compulsory pre-primary education from the age of four 
	Milestone
	Entry into force of the new Law regarding the gradual extension of free compulsory pre-primary education from the age of four years and adoption of aid schemes by the Council of Ministers
	Provision in the law(s) indicating the entry into force of the law(s)
	-
	-
	-
	Q4
	2023
	Entry into force of the Law which shall gradually (starting in the academic year 2024-2025 until academic year 2032-2033) reduce the entry age in free compulsory pre-primary education from the age of four years and eight months to four years. Adoption by the Council of Ministers of aid schemes to (a) cover tuition fees for the free compulsory pre-primary education in communal kindergartens, for children that cannot be enrolled in public kindergartens, and (b) subsidise tuition fees in private and communal kindergartens and nurseries, for the enrolment of children aged under the entry level of compulsory pre-primary education and above the age of four. 

	244
	C5.1R3
Gradual extension of free compulsory pre-primary education from the age of four 
	Target
	Children aged between 4 years and 4 years and 8 months enrolled in public, communal or private kindergartens
	 -
	Number
	0
	4 800
	Q2
	2026
	At least 4 800 children aged between 4 years and 4 years and 8 months are enrolled in public, communal or private kindergartens, or nurseries.

	245
	C5.1R3
Gradual extension of free compulsory pre-primary education from the age of four
	Target
	New places in new or extended public kindergartens
	 -
	Number
	0
	675 new places in public kindergartens
	Q2
	2026
	At least 675 new places in public kindergartens. 

	246a
	C5.1R4
Digital transformation of school units with the aim of supporting digital skills and skills related to STEM education

	Target
	Classrooms digitally equipped 
	 -
	Number
	0
	700
	Q2
	2024
	Classrooms in at least 700 schools have been digitally equipped with, for example, laptops, projectors, microphones, speakers, digital graphic boards, cameras, and TVs.

	246b
	C5.1R4
Digital transformation of school units with the aim of supporting digital skills and skills related to STEM education
	Target
	Support scheme for the digital equipment for pupils
	-
	Number
	0
	15 000
	Q2
	2026
	Supply or financial support for the purchase of digital equipment to 15 000 students. 

	249
	C5.1R5
E-skills Action Plan – Implementation of specific actions
	Milestone
	National e-Skills Action Plan is adopted by the Council of Ministers 
	National e-
Skills Action Plan is adopted by the Council of Ministers 

	
	
	
	Q4
	2021
	National e-Skills Action Plan is adopted by the Council of Ministers, which shall include at least:
• development of an e-learning platform, containing a 
self-assessment tool for digital fitness, index of all available skilling programmes, 
and content material on digital skills and cross-sectoral competences.
• design and delivery of programmes and interventions for professionals within the 
public sector in areas such as Project management, Microsoft tools, cybersecurity, social media, e-collaboration and productivity tools;
• investment in digital infrastructure.

	250
	C5.1R5
E-skills Action Plan – Delivery of specific actions
	Milestone
	Measures related to the e-Skills Action Plan 
	Programmes organised, approval of a communication plan

	-
	-
	-
	Q4
	2025
	- Trainings targeted at public sector employees for digital skills and project management.
- Receipt of digital equipment (for example laptops, computers).
- Approval of a communication plan for the promotion of digital skills.

	251
	C5.1I1
Construction of one Model Technical School
	Milestone
	Contract for the construction of one Technical School 
	Contract Signature and initiation of construction
	-
	-
	-
	Q4
	2022
	Signing of a contract with the contractor selected under a competitive call for proposals for the construction of one Technical School in Limassol and issue of construction initiation order by the project Engineer.

	254
	C5.1I2
Skilling, Reskilling and Upskilling 
	Target
	Trainings in programmes for digital, green, blue and entrepreneurial skills 
	 -
	Number
	0
	25 600
	Q4
	2025
	25 600 participants trained in programmes for digital, green, blue, and entrepreneurial skills.
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M. COMPONENT 5.2: LABOUR MARKET, SOCIAL PROTECTION AND INCLUSION
This component of the Cypriot Recovery and Resilience plan addresses: (i) inefficiencies and gaps in social protection notably for self-employed and people working in non-standard forms of employment, (ii) the lack of legislation for flexible working arrangements in the form of teleworking, (ii) challenges related to unemployment and youth unemployment and the high level of young people not in employment, education or training (NEETs), (iii) gaps in early childhood education and care (ECEC) and (iv) challenges with respect to social inclusion and welfare, including a high level of people at risk of poverty or social exclusion (AROPE) and increasing needs in long-term care. 
The reforms and investments included in the component address the country-specific recommendations on the public employment services and the education and training system (country specific recommendation 3 of 2019 and country specific recommendation 2 of 2020), providing social protection for all and introducing flexible working arrangements (country specific recommendation 2 of 2020), and improving the efficiency and digitalisation of the public sector (country specific recommendation 1 of 2019 and country specific recommendation 4 of 2020). 

M.1. 	Description of the reforms and investments for non-repayable financial support
Reform 2 (C5.2R2): Flexible work arrangements in the form of telework 
The objective of this reform is to support flexible work arrangements in the form of telework. 
This measure consists in the entry into force of a new legal act(s) for flexible work arrangements and a subsidy scheme for employers to hire unemployed persons who will partially telework.

Investment 1 (C5.2I1): Supporting the Department of Labour and Public Employment Services (PES) and reinforcing support for young people
The objective of this investment is enhancing support for unemployed persons.
This measure consists in digitalising the Department of Labour and Public Employment Services (PES) and a grant scheme.

Investment 2 (C5.2I2): Establishment of Multifunctional Centres and Childcare Centres 
The objective of this investment is to increase the labour market participation of carers (often women), and to enhance the availability of quality care and social infrastructure for children.
This measure consists in a scheme for multifunctional centres and childcare centres. 

Investment 3 (C5.2I3): Establishment of home structures for people in need of long-term care 
The objective of this investment is to address gaps in long-term care services. 
This measure consists in home structures for people in need of long-term care.

Investment 4 (C5.2I4): Child centres in municipalities 
The objective of this investment is to facilitate the participation of workers with caring responsibilities, in the labour market, and to enhance the social inclusion of children from disadvantaged and/or migrant background.
This measure consists in the construction of four (4) childcare centres.

Investment 5 (C5.2I5): Construction of two model special education schools 
The objective of this investment is to enhance the school environment for pupils with disabilities or other special educational needs and support them academically and socially. 
This measure consists in the construction of two special education schools in the Limassol district. 

Reform 1 (C5.2R1): Reform of the Social Insurance System and Restructuring of the Social Insurance Services 
The objective of this reform is to widen access to social protection and to support the Social Insurance Services. 
This measure consists in upgrading the Integrated Social Insurance Information System and in the extension of social insurance coverage . 
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M.2. 	Milestones, targets, indicators, and timetable for monitoring and implementation for non-repayable financial support
	Sequential Number
	Related Measure (Reform or Investment)
	Milestone / Target
	Name
	Qualitative indicators 
(for milestones)
	Quantitative indicators 
(for targets)
	Indicative timeline for completion
	Description of each milestone and target

	
	
	
	
	
	Unit of measure
	Baseline
	Goal
	Quarter
	Year
	

	255
	C5.2R2
Flexible Work Arrangements in the Form of Telework
	Milestone
	Entry into force of the law for flexible work arrangements in the form of telework
	Provision in the law indicating the entry into force of the law for the flexible work arrangements in the form of telework 
	-
	-
	-
	Q2
	2023
	Entry into force of a new law which shall regulate flexible work arrangements in the form of telework. The law shall include a definition of telework, description of the economic activities where telework is applicable, the conditions for taking up telework and the rights and obligations of employers and employees.

	256
	C5.2R2
Flexible Work Arrangements in the Form of Telework
	Target
	Grants disbursed to employers for hiring at least 300 persons 
	-
	Number
	0
	300
	Q3
	2025
	Grants disbursed to employers for hiring, for at least 6 months, at least 300 previously unemployed persons (including at least 140 women), including telework.

	258
	C5.2I1
Supporting the Department of Labour and Public Employment Services and reinforcing support for young people 
	Target
	Platform and systems accessible
	-
	Number
	0
	3
	Q4
	2024
	Platform and systems accessible for:
(1) hiring schemes of the Department of Labour, 
(2) Performance Management System for the Public Employment Services and 
(3) an early warning and tracking system for young people (aged 15-29) not in education, employment, or training (NEETs) for the Public Employment Services, 

	259
	C5.2I1
Supporting the Department of Labour and Public Employment Services and reinforcing support for young people 
	Target
	Grants disbursed to employers for hiring at least 450 young people not in employment or in education or training (NEETs) 
	-
	Number
	0
	450
	Q4
	2025
	Grants disbursed for hiring at least 450 young people (aged 15-29) not in employment, education, or training (NEETs), for at least 6-month period.

	261
	C5.2I2
Establishment of multifunctional centres and childcare centres
	Milestone
	Adoption of a national strategy on early childhood education and care (ECEC) and action plan 
	Adoption of a national strategy on ECEC and an action plan
	-
	-
	-
	Q4
	2024
	A national strategy and an action plan on enhancing early childhood education and care (ECEC) have been adopted by the Council of Ministers.

	263
	C5.2I2
Establishment of multifunctional centres and childcare centres
	Target
	Grant disbursed to at least 9 local authorities/ Non-Governmental Organisations for Multifunctional Centres or Childcare Centres
	-
	Number
	0
	9
	Q2
	2026
	Grant disbursed to at least 9 local authorities/ Non-Governmental Organisations for Multifunctional Centres or Childcare Centres.

	264
	C5.2I3
Establishment of Home structures for people in need of long-term care (LTC)
	Target
	Home structures for people in need of long-term care 
	 -
	Number
	0
	4
	Q2
	2026
	Completion certificate of at least 4 home structures for people in need of long-term care.

	266
	C5.2I4
Child Centres in Municipalities
	Target
	Construction of at least one child centre 
	-
	Number
	0
	1
	Q4
	2022
	Completion of construction and issue of taking-over certificate of at least one child centre in one of the following municipalities: Ayios Athanasios, Ayia Napa, Paralimni and Yermasoyia.

	267
	C5.2I4
Child Centres in Municipalities
	Target
	Construction of at least three child centres 
	-
	Number
	1
	4
	Q4
	2024
	Issuing of taking-over certificates of three child centres (one child centre in Amathounta, one in Ayia Napa and one in Paralimni -Deryneia). 

	268
	C5.2I5
Construction of Two Model Special Education Schools
	Milestone
	Signing of contract with the selected tenderer (contractor) 
	The contract shall be signed with the selected tenderer (contractor) 
	-
	-
	-
	Q4
	2022
	Signing of contract with the selected tenderer(s) (contractor (s)) selected under a competitive call for proposals for the construction of two model schools in Limassol - the Special Education School of Apostolos Loucas and the Red Cross Recovery Special Needs School.

	269
	C5.2I5
Construction of Two Model Special Education Schools
	Milestone
	Construction of two Special Education Schools
	Taking-over certificates 
	-
	-
	-
	Q4
	2025
	Taking-over certificates of two Special Education Schools in Limassol. 

	270
	C5.2R1
Reform of the Social Insurance System and Restructuring of the Social Insurance Services
	Milestone
	Entry into force of the revised Social Insurance Law
	Provision in the amending law indicating the entry into force of the revisions to the Social Insurance Law 
	
	
	
	Q4
	2024
	Entry into force of the revised Social Insurance Law, which shall incorporate the extension of the social insurance coverage to self-employed. 

	271
	C5.2R1
Reform of the Social Insurance System and Restructuring of the Social Insurance Services 
	Milestone
	Integrated Social Insurance Information System 
	Deliverables including a report, digital services, management information system 
	-
	-
	-
	Q2
	2026
	Integrated Social Insurance Information System including:
· a report on the current IT system, 
· interoperability with other systems, 
· digital services,
· management information system.
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N. COMPONENT 6.1: REPOWEREU
The REPowerEU chapter addresses the challenge of reducing reliance on fossil fuels. The objectives of the component are to strongly reduce Cyprus’ dependence from imported fossil fuels in general. The new RePowerEU chapter contributes to the achievement of Cyprus’s energy efficiency obligations and targets set for 2030, under the National Energy and Climate Plan. In order to limit its energy dependence, Cyprus shall further invest in energy efficiency improvements in buildings and road transport and accelerate the deployment of renewables.

The measures included in the REPowerEU chapter address most aspects of recent country-specific recommendations in the field of energy, as they shall foster research and innovation in the field of green transition and energy production, storage, transmission and distribution solutions, promote renewables and accelerate energy efficiency measures in various buildings in the public and private sector, enhance the regulatory framework for the operation of Energy Communities, and promote widespread use of Electric Vehicles.

It is expected that no measure in this component does significant harm to environmental objectives within the meaning of Article 17 of Regulation (EU) 2020/852, taking into account the description of the measures and the mitigating steps set out in the recovery and resilience plan in accordance with the ‘Do no significant harm’ Technical Guidance (2021/C58/01).

The implementation of the measures is expected to contribute to reducing dependency on fossil fuels. Increasing the share of renewable energy sources has a cross-border and multi-country dimension because it contributes to securing the energy supply in the Union as a whole. 

N.1. 	Description of the reforms and investments for non-repayable financial support
Reform 1 (C6.1R1) Regulating and facilitating the participation of citizens in the electricity market 
The objective of this reform is the participation of citizens in the national energy market. 
This measure consists in creating a contact point for citizens to participate in the electricity market. 

Reform 2 (C6.1R2) Introduction of regulatory framework for the connection of EV recharging points to the distribution network
The objective of this reform is to provide the regulatory framework for the procurement of flexibility services by the DSO as well as the connection of EV Charging Points to the Distribution Network. 
This measure consists in the entry into force of regulatory decision(s) for EV charging points. 

Investment 1 (C6.1I1). Scaled-up measure: Renewables and individual energy efficiency measures in dwellings 
The objective of this investment is to scale up Investment C2.1I2: Promoting renewables and individual energy efficiency measures in dwellings and tackling energy poverty, including in households with vulnerable electricity consumers under Component 2.1. 
The scaled-up part of this measure consists in increasing the number of dwellings that invested in their energy performance.

Investment 3 (C6.1I3) Promoting extensive energy renovations of dwellings 
The objective of this investment is to reduce energy consumption and CO2 emissions in dwellings. 
This measure consists in energy renovations in at least 800 dwellings.

Investment 5 (C6.1I5). Scaled-up measure: Scheme for the competitiveness and the energy efficiency of large enterprises in Cyprus
The objective of this investment is to scale up Investment C3.1I7: Scheme for the competitiveness and/or the energy efficiency of large enterprises in Cyprus, under Component 3.1. 
This measure consists in providing support to large enterprises undertaking energy efficiency investments.

Investment 6 (C6.1I6). Scaled-up measure: Thematic research and innovation funding program on green transition
The objective of this investment is to scale up Investment C3.2I3: R&I funding program on green transition, under Component 3.2. 
The scaled-up part of this measure consists in projects on green transition R&I activities.

Investment 7 (C6.1I7). Thematic research in enterprises for energy production, storage, transmission, and distribution solutions
The objective of this investment is to find solutions to bottlenecks identified in energy production, storage, transmission, and distribution. 
This measure consists in projects on energy production, storage, transmission and distribution solutions R&I activities.
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N.2.	Milestones, targets, indicators, and timetable for monitoring and implementation for non-repayable financial support
	Sequential Number
	Related Measure (Reform or Investment)
	Milestone / Target
	Name
	Qualitative indicators 
(for milestones)
	Quantitative indicators 
(for targets)
	Indicative timeline for completion
	Description of each milestone and target

	
	
	
	
	
	Unit of measure
	Baseline
	Goal
	Quarter
	Year
	

	272
	C6.1R1 Regulating and facilitating the participation of citizens in the electricity market
	Milestone
	Single contact point for the participation of citizens in the electricity market 
	Publication of Council of Ministers’ Decision in the official gazette
	-
	-
	-
	Q4
	2025
	Publication in the official gazette of decision on the participation of renewable and citizens communities, active customers, and renewable self-consumers in the electricity market. 

	273
	C6.1R2 Establishment of the regulatory framework for the connection of EV charging points 
	Milestone
	Entry into force of Regulatory Decision/s on the connection of EV charging points 
	Publication of Regulatory Decision/s in the official gazette
	-
	-
	-
	Q4
	2025
	Entry into force of regulatory decision issued by CERA for the connection of Electric Vehicle Charging Points to the Distribution Network. Publication of the regulatory decision on procurement of flexibility services by the DSO. 

	29b
	C6.1I1 Scaled-up measure: renewables and individual energy efficiency measures in dwellings 
	Target
	Energy efficiency measures in dwellings and tackling energy poverty
	-
	Number
	29 300
	50 000
	Q2
	2026
	Reducing primary energy demand on average by at least 30% for 50 000 dwellings, including 7 100 vulnerable electricity consumers households.

	274
	C6.1I3 Promoting extensive energy renovations of dwellings
	Milestone
	Support scheme for energy upgrading of dwellings
	Publication of call for proposals for the support scheme
	-
	-
	-
	Q1
	2024
	Publication of the call for proposals for the support scheme for promoting extensive energy upgrading of dwellings, following Council of Ministers decision approving the scheme objectives, with the aim to achieve at least a 30% primary energy demand reduction.

	275
	C6.1I3 Promoting energy renovations of dwellings
	Target 
	Improving energy performance of dwellings
	-
	Number
	0
	800
	Q2
	2026
	Energy Performance certificates for 800 energy renovated dwellings, with the objective to achieve at least a 30% primary energy demand reduction on average, have been issued.

	102b
	C6.1I5 Scaled-up measure: Scheme for the competitiveness and the energy efficiency of large enterprises in Cyprus
	Target 
	Signature of grants with 12 enterprises
	-
	Number
	0
	12
	Q2
	2026
	[bookmark: _Hlk213778635]Signature of grant agreements with at least 12 enterprises. The projects shall be selected in a call that requires compliance with the ‘Do no significant harm’ Technical Guidance (2021/C58/01) through the use of an exclusion list excluding notably activities related to fossil fuels, including
downstream use.

	131b
	C6.1I6 Scaled-up measure: Thematic research and innovation funding program on green transition
	Target
	Projects on green transition R&I activities
	-
	
	10
	19
	Q2
	2026
	Reports issued by the RIF for at least 19 projects on green transition R&I activities.

	277
	C6.1I7 Thematic research in enterprises for energy production, storage, transmission, and distribution solutions
	Target
	Projects on energy production, storage, transmission, and distribution solutions R&I activities
	-
	Number
	0
	20
	Q2
	2026
	Reports issued by the RIF for at least 20 projects on energy production, storage, transmission, and distribution solutions R&I activities. The respective calls shall comply with the ‘Do Not Significant Harm’ Technical Guidance (2021/C58/01) through the use of an exclusion list.
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O. COMPONENT 7.1: AUDIT AND CONTROL 
This component aims to ensure that the control framework of the Cypriot recovery and resilience plan prevents, detects and corrects corruption, fraud and conflicts of interests when using the funds provided under the Recovery and Resilience Facility Regulation (RRF Regulation), as well as ensuring adequate arrangements to effectively avoid double funding under the RRF Regulation and other Union programmes. 

O.1. Description of the reforms and investments for non-repayable financial support
Reform 1 (C7.1R1): Arrangements for the control framework of the Recovery and Resilience Plan
[bookmark: _Hlk150338328]The objective of the measure is to improve the control framework of the Cypriot Recovery and Resilience Plan. To ensure an effective implementation of proportionate measures for the protection of the financial interests of the Union (PFIU) according to the Article 22 of the RRF Regulation, 
[bookmark: _Hlk150338194]The Council of Ministers shall adopt mandatory instructions prepared by the Coordination Authority and distributed upon their adoption to all relevant bodies. 
The milestone under this measure shall be fulfilled by the time of submission of the next payment request to the Commission following the adoption of this Implementing Decision and shall be a prerequisite for any future payment. 
The reform shall be completed by 31 December 2023.
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O.2. Milestones, targets, indicators, and timetable for monitoring and implementation for non-repayable financial support
	Sequential Number
	Related Measure (Reform or Investment)
	Milestone / Target
	Name
	Qualitative indicators 
(for milestones)
	Quantitative indicators 
(for targets)
	Indicative timeline for completion
	Description of each milestone

	
	
	
	
	
	Unit of measure
	Baseline
	Goal
	Quarter
	Year
	

	278
	C7.1R1 
Arrangements for the control framework of the Recovery and Resilience Plan
	Milestone
	Clear delimitation between control and implementation duties 
	Adopted instructions and proof of dissemination to all Implementing Bodies.
	-
	-
	-
	Q4
	2023
	The Council of Ministers shall adopt mandatory instructions prepared by the Coordinating Authority which shall cover at least the following areas: 
· The risk assessment methodology to be applied for all verification types (administrative and on the spot),
· Verifications for double funding and procedures for its avoidance, 
· The treatment of irregularities and the whistle blowing process followed for interventions (projects or schemes) funded by the Union, 
· Requirements for audit trail,
· A central fraud risk assessment for all contracting authorities, taking into consideration all the elements outlined in the Guidance Note on Fraud Risk Assessment and Effective and Proportionate Anti-Fraud Measures for ESIF 2014-2020. Each contracting authority functioning under the RRP is mandated to comply with the action plan devised by the central fraud risk assessment team.
· Establishment of specific functions for PFIU, dedicated to tackling issues related to fraud, corruption, and conflicts of interest in Implementing Bodies implementing aid schemes under the RRP.
The instructions shall be distributed to all entities involved in the implementation, monitoring and control of the RRP and shall clearly segregate their responsibilities, ensuring a clear separation between control and implementation duties and shall require that controls are conducted in alignment with them.
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Estimated total cost of the recovery and resilience plan
The estimated total cost of the recovery and resilience plan of Cyprus is EUR 1 022 123 510.
The estimated total cost of the REPowerEU chapter is EUR 104 580 000. In particular, the estimated total costs of the measures referred to in Article 21c(3), point (a) of Regulation (EU) 2023/435 is EUR 0 whilst the costs of the other measures in the REPowerEU chapter is EUR 104 580 000.
SECTION 2: FINANCIAL SUPPORT
1. Financial contribution 
The instalments referred to in Article 2(2) shall be organised in the following manner:
First Instalment (non-repayable support): 
	Sequential Number
	Related Measure (Reform or Investment)
	Milestone/Target
	Name

	
	
	
	

	21
	C2.1R2
Independence of Cyprus Transmission System Operator (TSOC) from the incumbent Electricity Authority of Cyprus
	Milestone
	Law for the Regulation of the Electricity Market of 2021

	23
	C2.1R4
Energy Storage Regulatory Framework
	Milestone
	Amendment of the Transmission and Distribution Rules (TDRs) and Trading and Settlement Rules (TSRs) 

	24
	C2.1I1
Promoting energy efficiency investments in SMEs and non-profit organisations
	Milestone
	Support scheme for Promoting energy efficiency investments in SME and non-profit organisations

	27
	C2.1I2
Promoting renewables and individual energy efficiency measures in dwellings and tackling energy poverty in households with vulnerable electricity consumers
	Milestone
	First call for proposals for Promoting renewables and individual energy efficiency measures in dwellings 

	30
	C2.1I3
Encouraging the use of renewables and energy savings by local/wider public authorities and facilitating the transition of local communities towards climate mitigation & adaptation
	Milestone
	First call for proposals to support local authorities in energy efficiency measures 

	93
	C3.1I2
Enhancement of isotopic database of traditional Cypriot products.
	Milestone
	Liquid Chromatography- Isotopic Ratio Mass Spectrometer (LC-IRMS) equipment

	109
	C3.1R4
Enhancement of circular economy in the Industry
	Milestone
	Approval of the National Action Plan for the Enhancement of Circular Economy in Cyprus 

	160
	C3.4R3
Introduce new framework for evaluation and selection process for filling public service vacancies and new regulations for the evaluation of employees’ performance
	Milestone
	Entry into force of legislation for the evaluation and selection process for public service vacancies and regulations for employees’ performance evaluation. 

	186
	C3.4I8
Upgrading the infrastructure of courts
	Milestone
	Extension of the Famagusta District Court

	188
	C3.4R10
Improving the legal and institutional framework for fighting corruption
	Milestone
	Entry into force of the law on Transparency in Decision-Making and Related Matters

	189
	C3.4R10
Improving the legal and institutional framework for fighting corruption
	Milestone
	Entry into force of the law to protect whistle-blowers

	192
	C3.5R2 
Framework and Action Plan for addressing NPLs
	Milestone
	Entry into force of the package of amending laws regarding credit acquiring companies (CAC) and credit servicers to improve the working environment for non-performing loans management

	232
	C4.2I1
Digitalisation in various Central Government Ministries – Services
	Milestone
	Repository system for audit and control: information for monitoring implementation of RRF

	249
	C5.1R5
E-skills Action Plan – Implementation of specific actions
	Milestone
	National e-Skills Action Plan is adopted by the Council of Ministers 

	
	
	Instalment Amount
	EUR 97 701 149



Second Instalment (non-repayable support): 
	Sequential Number
	Related Measure (Reform or Investment)
	Milestone/Target
	Name

	
	
	
	

	7
	C1.1I2
Cyprus Innovative Public Health information and communications technology (ICT) System 
	Milestone
	Influenza Sentinel Surveillance (ISS)System 

	35
	C2.1I5
Energy Efficiency Upgrading of public buildings
	Target
	Thermal insulation and photovoltaic systems installed in schools

	45
	C2.1I9
Forests fire protection
	Milestone
	Signing of 8 Agreements/ Contracts Signatures for the purchase of vehicles, equipment and provision of services and issue of call for tenders for the purchase of firefighting aircraft

	71
	C2.3I3 
Integrated Monitoring and Control Management System for the Water Development Department’s infrastructure
	Milestone
	Completion of the detailed requirements analysis and system design document

	87
	C3.1R2
On-line platform for improving the trade and information symmetry in the fresh produce supply chain
	Milestone
	Law on unfair practices in transactions in the local fresh produce market

	97
	C3.1I5
Creation of a National Commercial Identity and promotion of the traditional product “halloumi”
	Milestone
	Action Plans for (a) the “made in Cyprus” branding, and (b) for the promotion of the halloumi cheese

	105
	C3.1I9
Promotion of circular economy in hotel establishments
	Target
	Coaching scheme for circular economy

	122
	C3.2R2
Incentives for investments and human capital in R&I
	Milestone
	Tax exemption of legal entities for investing in innovative companies

	125
	C3.2I1
Set up and operate a central Knowledge Transfer Office (KTO)
	Milestone
	Launch of KTO 

	134
	C3.3R1
Facilitation of Strategic investments
	Milestone
	Law for strategic investments

	155
	C3.4R1
Enhance the administrative capacity and improve the functioning of public administration for better policy making and implementation
	Milestone
	Action Plan on the efficient management of human resource issues in the national public administration
 

	187
	C3.4R10
Improving the legal and institutional framework for fighting corruption
	Milestone
	Entry into force of the law establishing the Independent Authority against Corruption 

	207a
	C3.5R9 
Improving tax collection and effectiveness of the Tax Department
	Milestone
	Operation of VAT Services within an Integrated Tax Administration System (ITAS)

	214
	C4.1R1
Empower the National Regulatory Authority (OCECPR)
	Milestone
	Launch of the geographical survey and entry into force of secondary legislation 

	233
	C4.2I1
Digitalisation in various Central Government Ministries – Services
	Target
	Start of the digital upgrade of a number of central government ministries and departments

	278
	C7.1R1 
Arrangements for the control framework of the Recovery and Resilience Plan
	Milestone
	Clear delimitation between control and implementation duties

	
	
	Instalment Amount
	EUR 87 136 829






Third Instalment (non-repayable support): 
	Sequential Number
	Related Measure (Reform or Investment)
	Milestone
/Target
	Name

	
	
	
	

	5
	C1.1I1
New facilities for the Cyprus Blood Establishment and procurement of the latest technology attendant equipment
	Milestone
	Contract signature for the construction of the Cyprus Blood Establishment

	22
	C2.1R3
Digital One-Stop Shops to streamline RES projects permitting and to facilitate Energy Renovation in Buildings
	Milestone
	Fully operational IT platform 

	77a
	C2.3I5
Anti-flood and water collection measures
	Milestone
	Completion of construction works of drainage network and reconstruction of streets and pavements in areas of Nicosia

	85
	C3.1R1
Move agricultural practices from the 20th century to the 21st century by investing in a national centre for excellence in agri-tech
	Milestone
	Cooperation between the Agricultural 
Research Institute and higher education institution(s), for at least one MSc programme

	95
	C3.1I3
Upskill existing and future farmers
	Target
	Scholarships granted

	120
	C3.2R1
National R&I Policy and policy tools
	Milestone
	Adoption of the national R&I Strategy and of the Action Plan to implement it

	123
	C3.2R3
Policies to foster access to publicly funded research infrastructure and laboratories
	Milestone
	Digital registry to record and publish research infrastructure 

	127
	C3.2I2
Innovation funding programmes for start-ups, innovative companies and SMEs
	Milestone
	Signature of grant agreements for 50% of budget

	130
	C3.2I3
R&I funding program on green transition
	Milestone
	Signature of grant agreements for a R&I funding programme of EUR 6 mln budget

	136
	C3.3R2
Enhancing Fast-Track Business Activation Mechanism
	Milestone
	Establishment of an electronic system where investors can submit their online application

	143
	C3.3R6
Incentives to promote mergers and acquisitions.
	Milestone
	Action Plan for incentives for mergers and acquisitions

	151
	C3.3I6
State funded equity fund 
	Milestone
	Setup of the Fund

	173
	C3.4I4
Enhancing e-system for issuing building permits 
	Milestone
	Enhancement of the e-application environment of the Hippodamos System

	194
	C3.5R3
Strategy for addressing inadequacies of the property transaction system (title deeds)
	Milestone
	Extension of the New Planning and Building Permit Policy 

	195
	C3.5R3 
Strategy for addressing inadequacies of the property transaction system (title deeds)
	Milestone
	Entry into force of the amendment of the Sale of Property (Specific Performance) Law 

	199
	C3.5R5 
Action plan for the development of a liability monitoring register
	Milestone
	Action Plan for the development of a liability monitoring register 

	201
	C3.5R6 
Reinforcing and strengthening the insolvency framework
	Milestone
	Full implementation and full operation of the legal and institutional framework for insolvency 

	209
	C3.5R10 
Addressing Aggressive Tax Planning
	Milestone
	Entry into force of the law to tackle aggressive tax planning 

	224
	C4.2R1
Digital Services Factory
	Milestone
	Definition of the Service Delivery Model for the Digital Services Factory 

	251
	C5.1I1
Construction of one Model Technical School
	Milestone
	Contract for the construction of one Technical School

	266
	C5.2I4
Child Centres in Municipalities
	Target
	Construction of at least one child centre 

	268
	C5.2I5
Construction of Two Model Special Education Schools
	Milestone
	Signing of contract with the selected tenderer (contractor) 

	
	
	Instalment Amount
	EUR 103 036 204
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Fourth Instalment (non-repayable support): 
	Sequential Number
	Related Measure (Reform or Investment)
	Milestone/
Target
	Name

	
	
	
	

	3
	C1.1R2
Design of an Electronic platform for the surveillance of Nosocomial Antibiotic Consumption and Healthcare – Associated Infections 
	Milestone
	Adoption of the list of health care facilities 

	43
	C2.1I8
Monitoring and reduction of GHG emissions in agriculture
	Milestone
	Purchase and installation of monitoring units for measuring GHG emissions from agriculture

	48
	C2.1I10
Market Management System to facilitate the opening of the electricity market to competition
	Milestone
	Installation of the Market Management System 

	74a
	C2.3I4
Smart Water and Sewerage Networks Management
	Target
	Delivery and installation of photovoltaics at the Larnaca Wastewater Treatment Plant

	86
	C3.1R1
Move agricultural practices from the 20th century to the 21st century by investing in a national centre for excellence in agri-tech
	Milestone
	Masters in the wider domain of Agriculture

	132
	C3.2I4
Funding to organisations performing R&D activities on dual technologies
	Milestone
	Signing of grant agreements which commit 80% of total budget for funding to organisations performing R&D activities on dual technologies

	135
	C3.3R1
Facilitation of Strategic investments
	Milestone
	Organisational capacity’s enhancement for the facilitation of strategic investments

	140
	C3.3R4
Design and establish a National Promotional Agency 
	Milestone
	Approval by the Council of Ministers of the roadmap for the creation and establishment of a National Promotional Agency

	147
	C3.3I4
Scheme for the digital upgrade of enterprises 
	Milestone
	Publication of call for proposals following approval of the scheme by the Council of Ministers

	158
	C3.4R2
Regulate flexible working arrangements in the public sector 
	Milestone
	Decision on flexible working arrangements in the public sector

	193
	C3.5R3 
Strategy for addressing inadequacies of the property transaction system (title deeds)
	Target
	 Reduction of backlog of cases for issuance of title deeds either by issuing title deeds or by rejecting the case 

	197
	C3.5R4 
New legal framework and system of exchange of data and credit bureau
	Milestone
	Entry into force of the framework and system of exchange of data legislation 

	220
	C4.1I2
Upgrade internet connection to be “Gigabit-ready” and promote connectivity take-up 
	Target
	Expansion of Gigabit-ready internet connection take-up by households

	229
	C4.2R3
Police Procedures digitalisation on Digipol
	Milestone
	Digipol prototype operational 

	236
	C4.2I2
Digitalisation of the Cyprus Ports Authority
	Target
	Start of the digital upgrade of the Cyprus Ports Authority

	255
	C5.2R2
Flexible Work Arrangements in the Form of Telework
	Milestone
	Entry into force of the law for flexible work arrangements in the form of telework

	
	
	Instalment Amount
	EUR 89 251 156



Fifth Instalment (non-repayable support): 
	Sequential Number
	Related Measure (Reform or Investment)
	Milestone/
Target
	Name

	
	
	
	

	9
	C1.1I3
Purchase/replacement of medical equipment in hospitals
	Target
	Health institutions having benefitted from the financial support scheme 

	13
	C1.1I6
Deployment of generic cross border e-health services in Cyprus
	Milestone
	Completion of the analysis, design and development phase of the IT System for cross-border e-health services

	28a
	C2.1I2
Promoting renewables and individual energy efficiency measures in dwellings and tackling energy poverty in households with vulnerable electricity consumers
	Target
	Dwellings and households with vulnerable electricity consumers (including people with disabilities) having improved their energy performance 

	36
	C2.1I5
Energy Efficiency Upgrading of public buildings
	Target
	Completion of set up and installation of photovoltaics system at the Nicosia General Hospital 

	38
	C2.1I6
Upgrading renewable energy and smart grids testing infrastructure at the University of Cyprus
	Milestone
	Signature of contracts for the installation of equipment to upgrade the electricity grid into a smart grid

	55
	C2.2R3
Progressively phase out the most polluting vehicles, especially in polluted urban areas
	Milestone
	Entry into force of the legislative act related to the phasing out of the most polluting vehicles

	100
	C3.1I7
Scheme for the enhancement of the competitiveness and/or the energy efficiency of large enterprises in Cyprus
	Milestone
	Start of the grant scheme on large enterprises

	112
	C3.1I12
Waste management towards circular economy 
	Milestone
	Signature of the contract for the installation of Green kiosks

	128
	C3.2I2
Innovation funding programmes for start-ups, innovative companies and SMEs
	Target
	Completed projects to carry out R&I related activities

	156
	C3.4R1
Enhance the administrative capacity and improve the functioning of public administration for better policy making and implementation
	Milestone
	New human resources management framework for Cyprus Police 

	163
	C3.4R5
Enhancement of the capacity of the Law Office 
	Milestone
	New IT system for the Law Office

	167
	C3.4I3
Economic Policy Modelling Hub 
	Milestone
	Setting up a Modelling Hub for Economic Policy Analysis

	180
	C3.4R8
Efficiency of Justice
	Milestone
	Entry into force of new Rules of Civil Procedure

	196
	C3.5R3 
Strategy for addressing inadequacies of the property transaction system (title deeds)
	Milestone
	Review of the Streets and Building Law

	203
	C3.5R7 
Strategy for Combating Financial Illiteracy
	Milestone
	Strategy for Combating Financial Illiteracy

	205
	C3.5R8 
Enhancing supervision of Insurance and Pension Funds
	Milestone
	Supervisory tools including data collection and analysis tool

	206
	C3.5I1 
Enhancement of the Supervisory Function of the Cyprus Securities and Exchange Commission
	Milestone
	Digital system for supervision of transactions for the Cyprus Securities and Exchange Commission 

	207b
	C3.5R9 Improving tax collection and effectiveness of the Tax Department
	Milestone
	Purchase of the new building for the integrated Nicosia District Office and Large Taxpayers’ Office

	212
	C3.5I2 Modernisation of Customs and Electronic Payment System 
	Target
	Putting into operation the information systems– envisaged under the Union Customs Code (UCC)

	217
	C4.1I1
Expansion of Very High Capacity Networks in underserved areas
	Milestone
	Start of very high capacity networks’ deployment in underserved areas

	225
	C4.2R1
Digital Services Factory
	Target
	Expansion of delivery of government services online through the Digital Services Factory

	231
	C4.2R4
Setting up the beneficial ownership registry
	Milestone
	Beneficial ownership registry available for use 

	243
	C5.1R3
Gradual extension of free compulsory pre-primary education from the age of four 
	Milestone
	Entry into force of the new Law regarding the gradual extension of free compulsory pre-primary education from the age of four years and adoption of aid schemes by the Council of Ministers

	
	
	Instalment Amount
	EUR 88 089 650
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Sixth Instalment (non-repayable support): 
	Sequential Number
	Related Measure (Reform or Investment)
	Milestone / Target
	Name

	
	
	
	

	40
	C2.1I7
Mass installation by the Distribution System Operator (DSO) of Smart Metering Infrastructure (Advanced Metering Infrastructure)
	Milestone
	Contract Signature for smart electricity metering infrastructure

	52
	C2.2R1
Installation of an Intelligent Transport System using Digital Twin technologies
	Target
	Installation and connection to the National Access Point of at least 150 sensors

	78
	C2.3I5
Anti-flood and water collection measures
	Milestone
	Construction works for the rainwater collection and recycling system in Kladeri area

	80
	C2.3I6
Water security projects
	Target
	Construction of two glass lined steel reservoirs in Nicosia district

	103
	C3.1I8
Added value of tourism 
	Target
	Grant agreements signed with enterprises in the hospitality sector 

	144
	C3.3I2
A Regulatory Sandbox
	Milestone
	Regulatory Sandbox 

	169
	C3.4R6
New legal framework for Local Authorities and support measures 
	Milestone
	New legal framework on local authorities

	171
	C3.4R7
Urban land consolidation 
	Milestone
	Entry into force of the law on urban land consolidation 

	181
	C3.4R8
Efficiency of Justice
	Target
	Reducing the backlog of cases and appeals

	216
	C4.1R2
Simplification of the administrative procedures for the deployment of VHCN 
	Milestone
	Entry into force of the administrative acts for very high capacity networks’ deployment

	246a
	C5.1R4
Digital transformation of school units with the aim of supporting digital skills and skills related to STEM education
	Target
	Classrooms digitally equipped 

	274
	C6.1I3 Promoting extensive energy renovations of dwellings
	Milestone
	Support scheme for energy upgrading of dwellings

	8
	C1.1I2
Cyprus Public Health information System
	Target
	Sentinels registered in the module

	237
	C4.2I2
Digitalisation of the Cyprus Ports Authority
	Target
	IT infrastructure of the Cyprus Ports Authority

	107
	C3.1I10
Enrichment of tourism 
	Milestone
	Aphrodite Route

	88
	C3.1R2
On-line platform for trade and information symmetry in the fresh produce supply chain
	Milestone
	Platform for recording transactions in the local fresh produce market

	17
	C1.1I5 
Construction works and new equipment in Cyprus State Hospitals
	Target
	Construction works or purchase of equipment in Cyprus State hospitals

	153
	C3.3I1
Integrated Information system for the Department of Registrar of Companies and Intellectual Property
	Milestone
	System hardware, software and networking installation

	
	
	Instalment Amount
	EUR 24 637 332



Seventh Instalment (non-repayable support): 
	Sequential Number
	Related Measure (Reform or Investment)
	Milestone / Target
	Name

	
	
	
	

	39
	C2.1I6
Expansion of the renewable energy and smart grids testing infrastructure at the University of Cyprus
	Milestone
	Acceptance of renewable energy and smart grids testing equipment

	54
	C2.2R2 
Entry into force of legal act(s) regarding electric vehicle (EV) recharging infrastructure 

	Milestone
	Entry into force of legal act(s) related to electric vehicle charging points 

	 124
	C3.2R3
Support access to publicly funded research infrastructure
	Milestone
	National Policy of the Republic of Cyprus for Open Science Practices 

	159
	C3.4R2
Regulate flexible working arrangements in the public sector 
	Milestone
	Flexible working arrangements

	170
	C3.4R6
New legal framework for Local Authorities and support measures 
	Milestone
	Trainings 

	174
	C3.4I4
E-system for issuing building permits 
	Milestone
	Planning and control tool, project management tool. Software and hardware of Hippodamos 

	198
	C3.5R4 
Digital system for the exchange of data and the provision of credit scoring services
	Milestone
	Entry into force of legal act(s) on the ARTEMIS data exchange mechanism and ARTEMIS data exchange mechanism providing credit scoring services in User Acceptance Testing phase 

	200
	C3.5R5 
Framework for Management of Private Debt
	Milestone
	Entry into force of legal act(s) for the management of private debt.

	210
	C3.5R10 
Addressing Aggressive Tax Planning
	Milestone
	Entry into force of legal act(s) to tackle aggressive tax planning

	215
	C4.1R1
Empower the National Regulatory Authority (OCECPR)
	Milestone
	Web portal on broadband and infrastructure mapping

	227
	C4.2R2
New cloud policy with regard to government IT systems and services and infrastructure set-up
	Target
	Two data centres with hosting services for government IT systems

	239a
	C5.1R1
Addressing skills mismatch between education and labour market (Secondary and Higher Education)
	Milestone
	Measures included in the National Action Plan 

	258
	C5.2I1
Supporting the Department of Labour and Public Employment Services and reinforcing support for young people 
	Target
	Platform and systems accessible

	261
	C5.2I2
Establishment of multifunctional centres and childcare centres
	Milestone
	Adoption of a national strategy on early childhood education and care (ECEC) and action plan 

	267
	C5.2I4
Child Centres in Municipalities
	Target
	Construction of at least three child centres 

	270
	C5.2R1
Reform of the Social Insurance System and Restructuring of the Social Insurance Services
	Milestone
	Entry into force of the revised Social Insurance Law

	16
	C1.1R3 
Gradually shifting the healthcare provision and reimbursement framework towards value-based models.
	Milestone
	Value-based reimbursement to be reflected for primary and in-patient care 

	142a
	C3.3R8
The Provision of Crowdfunding Services for Business Law 
	Milestone
	Entry into force of the legislation on the Provision of Crowdfunding Services for Business Law

	6
	C1.1I1
Cyprus Blood Establishment
	Milestone
	Blood establishment facilities and equipment

	14
	C1.1I6
 Generic cross border e-health services in Cyprus
	Milestone
	 Cross-border patient data exchange 

	66
	C2.3R1 
Water Resource Management Reform
	Milestone
	Adoption and publication of an action plan on water resource management 

	84
	C2.3I8 
Protection of the marine ecosystem from hazards through oil spills
	Milestone
	Delivery, quality inspection to verify their operational effectiveness and acceptance of three vessels and two aerial spraying systems

	94
	C3.1I2
 Support of isotopic database of Cypriot food or drink products
	Target
	Products connected to the system

	111
	C3.1R5
 Waste management coordination unit in the Department of Environment
	Milestone
	Waste management coordination unit

	202
	C3.5R6 Reinforcing the insolvency framework
	Milestone
	Digital systems of the Department of Insolvency accessible

	221
	C4.1I2
Upgrade internet connection to be “Gigabit-ready” and promote connectivity take-up
	Target
	Gigabit-ready internet connection take-up by at least 82 000 households 

	241
	C5.1R2
A school evaluation system and formative evaluation of teachers
	Milestone
	Council of Ministers Decision for a new School Evaluation system and entry into force of the legal act(s) for the Formative Evaluation of Teachers 

	
	
	Instalment Amount
	EUR 138 994 773
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Eight Instalment (non-repayable support): 
	Sequential Number
	Related Measure (Reform or Investment)
	Milestone/
Target
	Name

	
	
	
	

	2b
	C1.1R1
National Centre for Clinical Evidence and Quality Improvement
	Milestone
	Platform for clinical protocols, guidelines or pathways

	4
	C1.1R2
Electronic platform for the surveillance of Nosocomial Antibiotic Consumption and Healthcare- Associated Infections
	Milestone
	Electronic platform 

	10
	C1.1I3
Support for the purchase of medical equipment in private hospitals
	Target
	Private hospitals purchased medical equipment with funding from the financial support scheme

	15
	C1.1I7
 Public warning system for emergency operations 
	Milestone
	Public warning system gone live ready for pilot operation

	26
	C2.1I1
 Energy saving investments in SMEs, and non-profit organisations
	Target
	Energy saving projects in buildings 

	37
	C2.1I5
Energy Efficiency investment in public buildings
	Target
	Installation of photovoltaic systems in Fire Service Properties

	44
	C2.1I8
Monitoring and reduction of GHG emissions in agriculture
	Target
	Reduction of GHG emissions from agriculture

	48a
	C2.1I10
Market Management System (MMS) to facilitate the opening of the electricity market to competition

	Milestone
	First financial transactions of the MMS

	53
	C2.2R1
 Installation of an Intelligent Transport System using Digital Twin technologies
	Target
	Installation and connection to the National Access Point of a total of 300 sensors

	70
	C2.3I2 
Water Treatment Plants
	Milestone
	Projects in Water Treatments Plants

	79
	C2.3I5
Anti-flood and water collection measures
	Milestone
	Landscaping of flood channel(s) in Livadia


	108
	C3.1I10
Enrichment of tourism 
	Target
	
Investments, including but not limited to construction works, equipment, information and communication services, and advisory services

	115
	C3.1I12
Waste management towards circular economy 
	Target
	Installation of green kiosks 

	126
	C3.2I1
Set up a central Knowledge Transfer Office (KTO)
	Target
	Progress report on the provision of knowledge transfer support services

	137
	C3.3R2
 Supporting Fast-Track Business Activation Mechanism
	Target
	 Investment application assessment through the platform

	 141
	C3.3R4
National Promotional Agency
	Milestone
	 Cyprus National Promotional Agency

	157
	C3.4R1
 Support the functioning of public administration

	Milestone
	Guidelines and manuals, legal act(s) and trainings on management of human resources in the public administration

	162
	C3.4R4
Digitalisation of public procurement
	Milestone
	E-procurement system 

	168
	C3.4I3
Economic Policy Modelling Hub 
	Target
	Report on the Project “Economic Policy Modelling Hub” 

	172
	C3.4R7
Urban land consolidation 
	Target
	Number of plans for urban land planning 

	185
	C3.4I7
Training of judges
	Milestone
	Training of judges 

	213
	C3.5I2 
Modernisation of Customs and Electronic Payment System 
	Target
	Information systems or functionalities

	219
	C4.1I1
Expansion of Very High Capacity Networks in underserved areas
	Milestone
	Very high capacity networks are accessible in areas of no interest to private investors


	228
	C4.2R2
New cloud policy with regard to government IT systems and services and infrastructure set-up
	Milestone
	Adoption of a national cloud policy by the Council of Ministers

	230
	C4.2R3
Police Procedures digitalisation (Digipol)
	Milestone
	Digipol accessible 

	235
	 C4.2I1 Digitalisation of Central Government Ministries or departments
	Target
	Delivery of digital systems of five central government ministries or departments

	238
	C4.2I2
Digitalisation of the Cyprus Ports Authority
	Target
	IT infrastructure of Cyprus Ports Authority

	250
	C5.1R5
 E-skills Action Plan – Delivery of specific actions

	Milestone
	Measures related to the e-Skills Action Plan 

	254
	C5.1I2
Skilling, Reskilling and Upskilling 
	Target
	Trainings in programmes for digital, green, blue and entrepreneurial skills

	256
	C5.2R2
Flexible Work Arrangements in the Form of Telework
	Target
	 Grants disbursed to employers for hiring at least 300 persons

	259
	C5.2I1
Supporting the Department of Labour and Public Employment Services and reinforcing support for young people 
	Target
	 Grants disbursed to employers for hiring at least 450 young people not in employment or in education or training (NEETs) 

	269
	C5.2I5
Construction of Two Model Special Education Schools
	Milestone
	Construction of two Special Education Schools

	272
	C6.1R1 Regulating and facilitating the participation of citizens in the electricity market
	Milestone
	Single contact point for the participation of citizens in the electricity market

	273
	C6.1R2 Establishment of the regulatory framework for the connection of EV charging points 
	Milestone
	Entry into force of Regulatory Decision/s on the connection of EV charging points

	154
	C3.3I1
Information system for the Department of Registrar of Companies and Intellectual Property
	Target
	Training courses 

	104c
	C3.1I8
Added value of tourism 
	Milestone
	Renovation works and equipment for Filoxenia Conference Centre

	191a
	C3.5R11
Legal framework for a National Sanctions Implementation Unit 

	Milestone
	Legal framework for a National Sanctions Implementation Unit 

	
	
	Instalment Amount
	EUR 125 604 020
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Ninth Instalment (non-repayable support): 
	Sequential Number
	Related Measure (Reform or Investment)
	Milestone/Target
	Name

	
	
	
	

	12
	C1.1I4
Accreditation of health institutions 
	Target
	Health institutions have received financial support for their accreditation

	19
	C2.1R1
Green Taxation 
	Milestone
	Entry into force of legal acts introducing a carbon tax on transport fuels, an increase of existing water fees, a charge on the landfill of municipal waste, and tax incentives for enterprises and individuals.

	32c
	C2.1I3
Facilitating the transition of local communities towards climate investments
	Target
	Grant scheme to support sustainable climate adaptation investments

	42
	C2.1I7
Mass installation by the Distribution System Operator (DSO) of Smart Metering Infrastructure (Advanced Metering Infrastructure)
	Target
	 Acceptance and installation of smart meters

	47
	C2.1I9
Fire protection
	Milestone
	Acceptance of firefighting aircraft vehicles and equipment

	61
	C2.2I2
Creation of electro-mobility infrastructure
	Target
	Installation or delivery of charging points 

	63a
	C2.2I3
Advance the use of Electric Vehicles (EVs)
	Target
	Purchase and registration of electric vehicles and electric bicycles

	65
	C2.2I3
Advance the use of Electric Vehicles (EVs)
	Target
	Scrapping of high emission vehicles

	76b
	C2.3I4
Smart Water and Sewerage Networks Management
	Milestone
	Projects in Larnaca and Limassol

	90
	C3.1R3
Genetic improvement of the Cyprus sheep and goat population
	milestone
	Genomic identification registered in ARI database.

	99
	C3.1I6
Scheme for supporting the production of enterprises in agricultural sector
	Target
	Grant agreements signed with enterprises in the agricultural sector

	102a
	C3.1I7
Scheme for the competitiveness and/or the energy efficiency of large enterprises in Cyprus 
	Target
	Grant agreements signed with enterprises

	104
	C3.1I8
Added value of tourism
	Target
	Grant to hotels or other tourism establishments

	106
	C3.1I9
Circular economy in hotel establishments
	Target
	Certified circular hotels

	110
	C3.1R4
Circular economy
	Target
	Signed grant agreement with companies which are moving into a circular operating model

	121
	C3.2R1
National Research and Innovation Policy 
	Milestone
	Performance-based funding mechanism; open access policy framework for publicly funded research and technological infrastructure; framework for monitoring and coordinating the participation in ESFRI Landmarks

	129
	C3.2I2
Innovation funding programmes
	Target
	Projects on R&I activities

	131a
	C3.2I3
R&I funding program on green transition
	Target
	Projects on green transition R&I activities

	133
	C3.2I4
Funding schemes for R&D activities on dual-use technologies and classified laboratories 
	Target
	At least 16 facility security clearance certificates issued.

	148
	C3.3I4
Scheme for the digital upgrade of enterprises 
	Target
	Grant agreements signed 

	152
	C3.3I6
State funded equity fund 
	Target
	Investees supported through the Fund

	176
	C3.4I5
Smart cities 
	Target
	Mobile applications and smart sensors

	178
	C3.4I6a
Regeneration and Revitalisation of Nicosia Inner City 
	Target
	Renovation of rooms in Nicosia 

	183
	C3.4R9
Digital transformation of courts
	Milestone
	i-justice system

	208
	C3.5R9 Digitalising tax collection 
	Milestone
	Direct tax administration services of the Tax department within the ITAS

	211
	C3.5R10 
Addressing Aggressive Tax Planning
	Milestone
	Entry into force of legal act(s) addressing aggressive tax planning

	226
	C4.2R1
Digital Services Factory 
	Target
	At least 70 services through the Digital Services Factory

	239b
	C5.1R1
Addressing skills mismatch between education and labour market (Secondary and Higher Education)
	Target
	In-job shadowing programme 

	239c
	C5.1R1
Addressing skills mismatch between education and labour market (Secondary and Higher Education)
	Target
	Laboratories equipped 

	244
	C5.1R3
Gradual extension of free compulsory pre-primary education from the age of four
	Target
	Children aged between 4 years and 4 years and 8 months enrolled in public, communal and private kindergartens 

	245
	C5.1R3
Gradual extension of free compulsory pre-primary education from the age of four
	Target
	New places in new or extended public kindergartens

	246b
	C5.1R4
Digital transformation of school units with the aim of enhancing digital skills and skills related to STEM education
	Target
	Support scheme for the digital equipment for pupils

	263
	C5.2I2
Establishment of multifunctional centres and childcare centres
	Target
	Grant disbursed to at least 9 local authorities/ Non-Governmental Organisations for Multifunctional Centres or Childcare Centres

	29b
	C6.1I1 Scaled-up measure: Promoting renewables and individual energy efficiency measures in dwellings 
	Target
	Energy efficiency measures in dwellings and tackling energy poverty

	275
	C6.1I3 Promoting energy renovations of dwellings
	Target
	Improving energy performance of dwellings

	102b
	C6.1I5 Scaled-up measure: Scheme for the enhancement of the competitiveness and the energy efficiency of large enterprises in Cyprus
	Target
	Signature of grants with 12 enterprises

	131b
	C6.1I6 Scaled-up measure: Thematic research and innovation funding program on green transition
	Target
	Projects on green transition R&I activities

	277
	C6.1I7 Thematic research in enterprises for energy production, storage, transmission and distribution solutions
	Target
	Projects on energy production, storage, transmission and distribution solutions R&I activities

	81
	C2.3I6
Water security projects
	Target
	Water reservoir(s) and water treatment plant 

	77b
	C2.3I5
Anti-flood and water collection measures
	Milestone
	Anti-flood work(s) or reconstruction or constructions of streets and pavements in Nicosia and Limmasol

	18
	C1.1I5 
Construction works and new equipment in Cyprus State Hospitals
	Target
	Construction works or purchase of equipment in Cyprus State hospitals 

	264
	C5.2I3
Establishment of Home structures for people in need of long term care (LTC) 
	Target
	Home structures for people in need of long-term care

	204
	C3.5R8 
Enhancing supervision of Insurance and Pension Funds
	Target
	Employment of additional permanent employees of the Registrar of Occupational Retirement Benefits Fund (RORBF) and the Insurance Companies Control Service (ICCS)

	138a
	C3.3R7
Screening of Foreign Direct Investment
	Milestone
	Entry into force of the legal act(s) on foreign Direct Investment screening

	28b
	C2.1I2
Renewables and individual energy efficiency measures in dwellings and tackling energy poverty in households with vulnerable electricity consumers
	Target
	Energy efficiency measures in dwellings

	116b
	C3.1I11 Extension of the Cyprus Green Points Network 
	Target
	Construction or extension of six Green Points

	271
	C5.2R1
Reform of the Social Insurance System and Restructuring of the Social Insurance Services 
	Milestone
	Integrated Social Insurance Information System.

	58
	C2.2I1
Sustainable Urban Mobility Projects (SUMP) and accessibility enhancing measures
	Target
	Construction work for at least 35 km of sustainable transport routes

	
	
	Instalment Amount
	EUR 265 772 568
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SECTION 3: ADDITIONAL ARRANGEMENTS 
1. Arrangements for monitoring and implementation of the recovery and resilience plan
The monitoring and implementation of the recovery and resilience plan of Cyprus has been set out in the Council of Ministers decision of 14 May 2021, which approved the plan. They shall take place in accordance with the following arrangements: 
· [bookmark: _Ref74300103]The Monitoring Committee, chaired by the Director General of the Directorate General Growth, Ministry of Finance and attended by the Directors-General of Ministries and Deputy Ministries involved in the plan, shall be responsible for centrally monitoring progress in implementation, resolving issues and responding to risks at the highest technical level. It shall convene at least before each submission to the Commission of requests for payment and progress reports provided for under Regulation (EU) 2021/241. It may rely on reporting and other support from the Coordinating Authority.
· The Coordinating Authority, which is the Directorate for Recovery and Resilience of the Directorate General Growth, shall be responsible for the monitoring and implementation of the recovery and resilience plan at operational level. Specifically, the Coordinating Authority is responsible for monitoring, verifying and certifying the achievement of the milestones and targets of measures of the plan and ensuring the timely submission of all information described in Article 22(2), point (d) of Regulation (EU) 2021/241. In performing its monitoring functions, the Coordinating Authority is assisted by two specialised Monitoring Bodies designated for specific measures of the plan. 
· The National Control and Audit Coordinator for the implementation of the plan, which is the Verifications and Certification Directorate of the Treasury of the Republic of Cyprus, shall be responsible for supporting the Coordinating Authority in overseeing controls by all stakeholders, including Implementing Bodies, in accordance with the management and control system of the plan and the national and EU legislation. In that respect, it shall also monitor the status of the findings of ex post audits, acting as the intermediate body between the Coordinating Authority and the Internal Audit Service of the Republic of Cyprus and the Audit Office of the Republic of Cyprus (together, “the audit bodies”). The National Control and Audit Coordinator shall not be involved in the planning and execution of the audits, which is within the sole responsibility of the audit bodies. It shall manage and process all information described in Article 22(2), point (d) of Regulation (EU) 2021/241, collected by the Implementing Bodies. In this respect, it has the responsibility to oversee the treatment of serious irregularities, meaning fraud, corruption and conflicts of interests, and ensure that double funding is avoided through controls of the information submitted by the Implementing Bodies. 
· The Implementing Bodies shall have the first line responsibility to prevent, detect, report and correct conflicts of interest, corruption and fraud, and avoid double funding. To that end, they shall undertake first level controls and verifications of the physical and financial aspect of the measures under their responsibility and regularly update the Coordinating Authority and the specialised Monitoring Bodies, where relevant, regarding progress in achieving the milestones and targets of the measures under their responsibility and by providing all the necessary supporting documentation.
· The Internal Audit Service of the Republic of Cyprus is responsible for conducting ex post internal audits in any central government body including the audit of the achievement of milestones and targets of the plan, through an appropriate sampling method. The Audit Office of the Republic of Cyprus is responsible for conducting financial, performance and compliance ex post (and in some cases real time) external audits for projects implemented under the national budget through an appropriate sampling method which complies with the International Organisation of Supreme Audit Institutions (INTOSAI) standards. It shall be ensured that the selected sample necessarily includes a sufficient number of measures implemented through the recovery and resilience plan. 
· The Coordinating Authority shall be the body drawing up the requests for payment to the European Commission. The Coordinating Authority shall be supported by the National Control and Audit Coordinator in retrieving the results of audit procedures undertaken by the audit bodies (including the Internal Audit Service and the Audit Office), as well as all cases of serious irregularities, including cases of fraud or suspicion of fraud, corruption and conflicts of interest, that shall feed into the summary of audits, which shall accompany payment applications. 

Arrangements for providing full access by the Commission to the underlying data
A dedicated Monitoring Information System (MIS) shall be used by the Directorate for Recovery and Resilience of the Directorate General Growth for the implementation of the plan. Its core functionalities, or a contingent repository system with the required functionalities, shall be in place as attested by an audit report by 31 March 2022. In terms of required functionalities, a repository system shall record and store the relevant data related to the implementation of the recovery and resilience plan, in particular on the achievement of milestones and targets, data on final recipients, contractors, subcontractors and beneficial owners in line with Article 22(2), point (d), sections (i) to (iii) of Regulation (EU) 2021/241, by the first payment request.
In accordance with Article 24(2) of Regulation (EU) 2021/241, upon completion of the relevant agreed milestones and targets in Section 1 of this Annex, Cyprus shall submit to the Commission a duly justified request for payment of the financial contribution and of the loan. Cyprus shall ensure that, upon request, the Commission has full access to the underlying relevant data that supports the due justification of the request for payment, both for the assessment of the request for payment in accordance with Article 24(3) of Regulation (EU) 2021/241 and for audit and control purposes.
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